## Budget vs Actual
project_id | project_name | cost_category | revised_budget | original_budget_missing_flag | orphan_project_flag | pending_exposure | incurred_cost | budget_remaining | no_matching_transactions_flag |  | Import validation total
P001 | Juniper Retail 01 | Labor | 357667.87 | FALSE | FALSE | 0 | 380205.32 | -22537.45 | FALSE | Revised budget | 119564833.67
P004 | Juniper Medical 04 | Labor | 251511.7 | FALSE | FALSE | 0 | 253196.12 | -1684.42 | FALSE | Pending exposure | 7961647.6
P006 | Granite Commons 06 | Labor | 321425 | FALSE | FALSE | 0 | 342577.2 | -21152.2 | FALSE | Incurred cost | 111386073.69
P011 | Granite Residences 11 | Labor | 207500 | FALSE | FALSE | 0 | 228514.24 | -21014.24 | FALSE
P013 | Aspen Renovation 13 | Labor | 487828 | FALSE | FALSE | 0 | 548428.71 | -60600.71 | FALSE
P016 | Wasatch Lodge 16 | Labor | 115179.12 | FALSE | FALSE | 0 | 128738.07 | -13558.95 | FALSE
P033 | Bonneville Retail 33 | Labor | 229635 | FALSE | FALSE | 0 | 226768.31 | 2866.69 | FALSE
P026 | Granite Commons 26 | Labor | 794870.57 | FALSE | FALSE | 0 | 848008.95 | -53138.38 | FALSE
P077 | Canyon Residences 77 | Labor | 223530.3 | FALSE | FALSE | 0 | 194001.95 | 29528.35 | FALSE
P083 | Wasatch Renovation 83 | Labor | 278750 | FALSE | FALSE | 0 | 281055.45 | -2305.45 | FALSE
P095 | Summit Lodge 95 | Labor | 143100 | FALSE | FALSE | 0 | 115982.45 | 27117.55 | FALSE
P003 | Summit Center 03 | Labor | 335861.72 | FALSE | FALSE | 0 | 322068.22 | 13793.5 | FALSE
P034 | Bonneville Office 34 | Labor | 134350 | FALSE | FALSE | 0 | 145925.14 | -11575.14 | FALSE
P038 | Canyon Renovation 38 | Labor | 173804.56 | FALSE | FALSE | 0 | 196563.94 | -22759.38 | FALSE
P039 | Granite Commons 39 | Labor | 156843 | FALSE | FALSE | 0 | 168591.27 | -11748.27 | FALSE
P058 | Bonneville Medical 58 | Labor | 106947 | FALSE | FALSE | 0 | 111290.41 | -4343.41 | FALSE
P063 | Summit Office 63 | Labor | 291896.73 | FALSE | FALSE | 0 | 320948.21 | -29051.48 | FALSE
P066 | Canyon Medical 66 | Labor | 161220.41 | FALSE | FALSE | 0 | 152467.83 | 8752.58 | FALSE
P076 | Granite Center 76 | Labor | 276461.75 | FALSE | FALSE | 0 | 259387.36 | 17074.39 | FALSE
P078 | Aspen Residences 78 | Labor | 324461.84 | FALSE | FALSE | 0 | 288783.63 | 35678.21 | FALSE
P091 | Granite Medical 91 | Labor | 466769.42 | FALSE | FALSE | 0 | 443188.51 | 23580.91 | FALSE
P093 | Granite Office 93 | Labor | 639054 | FALSE | FALSE | 0 | 493959.88 | 145094.12 | FALSE
P048 | Bonneville Office 48 | Labor | 141958.7 | FALSE | FALSE | 0 | 153477.31 | -11518.61 | FALSE
P049 | Wasatch Commons 49 | Labor | 258379.56 | FALSE | FALSE | 0 | 300859.37 | -42479.81 | FALSE
P068 | Aspen Lodge 68 | Labor | 266846.86 | FALSE | FALSE | 0 | 281462.42 | -14615.56 | FALSE
P074 | Copper Center 74 | Labor | 324875 | FALSE | FALSE | 0 | 341953.24 | -17078.24 | FALSE
P084 | Bonneville Renovation 84 | Labor | 238550 | FALSE | FALSE | 0 | 203749.14 | 34800.86 | FALSE
P087 | Copper Office 87 | Labor | 609458.16 | FALSE | FALSE | 0 | 275097.01 | 334361.15 | FALSE
P009 | Wasatch Retail 09 | Labor | 149472 | FALSE | FALSE | 0 | 167957.95 | -18485.95 | FALSE
P029 | Copper Center 29 | Labor | 183657.74 | FALSE | FALSE | 0 | 201506.88 | -17849.14 | FALSE
P055 | Canyon Lodge 55 | Labor | 318575 | FALSE | FALSE | 0 | 385435.06 | -66860.06 | FALSE
P023 | Summit Office 23 | Labor | 663702 | FALSE | FALSE | 0 | 747948.32 | -84246.32 | FALSE
P031 | Summit Lodge 31 | Labor | 132750 | FALSE | FALSE | 0 | 147458.69 | -14708.69 | FALSE
P044 | Copper Medical 44 | Labor | 124308 | FALSE | FALSE | 0 | 135948.64 | -11640.64 | FALSE
P047 | Granite Lodge 47 | Labor | 497508 | FALSE | FALSE | 0 | 518249.32 | -20741.32 | FALSE
P054 | Granite Office 54 | Labor | 129291.68 | FALSE | FALSE | 0 | 124103.28 | 5188.4 | FALSE
P012 | Canyon Retail 12 | Labor | 258442.69 | FALSE | FALSE | 0 | 289027.27 | -30584.58 | FALSE
P035 | Aspen Office 35 | Labor | 260475 | FALSE | FALSE | 0 | 269743.23 | -9268.23 | FALSE
P061 | Summit Center 61 | Labor | 515725.36 | FALSE | FALSE | 0 | 597150.22 | -81424.86 | FALSE
P071 | Wasatch Office 71 | Labor | 146468.68 | FALSE | FALSE | 0 | 157165.06 | -10696.38 | FALSE
P090 | Canyon Office 90 | Labor | 244715.61 | FALSE | FALSE | 0 | 243377.43 | 1338.18 | FALSE
P007 | Wasatch Renovation 07 | Labor | 486980.52 | FALSE | FALSE | 0 | 564976.26 | -77995.74 | FALSE
P008 | Bonneville Renovation 08 | Labor | 510180 | FALSE | FALSE | 0 | 516933.34 | -6753.34 | FALSE
P020 | Wasatch Commons 20 | Labor | 233191.54 | FALSE | FALSE | 0 | 240842.8 | -7651.26 | FALSE
P028 | Copper Office 28 | Labor | 63992.85 | FALSE | FALSE | 0 | 66599.54 | -2606.69 | FALSE
P043 | Granite Medical 43 | Labor | 232942.18 | FALSE | FALSE | 0 | 239536.13 | -6593.95 | FALSE
P046 | Granite Lodge 46 | Labor | 261515.28 | FALSE | FALSE | 0 | 303768.71 | -42253.43 | FALSE
P056 | Wasatch Office 56 | Labor | 97167.27 | FALSE | FALSE | 0 | 94882.43 | 2284.84 | FALSE
P065 | Aspen Lodge 65 | Labor | 169650 | FALSE | FALSE | 0 | 188173.78 | -18523.78 | FALSE
P075 | Granite Lodge 75 | Labor | 542516 | FALSE | FALSE | 0 | 533592.52 | 8923.48 | FALSE
P080 | Aspen Lodge 80 | Labor | 117882 | FALSE | FALSE | 0 | 102797.9 | 15084.1 | FALSE
P094 | Copper Commons 94 | Labor | 424450.05 | FALSE | FALSE | 0 | 210526.09 | 213923.96 | FALSE
P041 | Canyon Office 41 | Labor | 333073.87 | FALSE | FALSE | 0 | 354093.87 | -21020 | FALSE
P050 | Granite Lodge 50 | Labor | 291490.92 | FALSE | FALSE | 0 | 329597.89 | -38106.97 | FALSE
P051 | Aspen Retail 51 | Labor | 115614 | FALSE | FALSE | 0 | 125173.86 | -9559.86 | FALSE
P018 | Wasatch Renovation 18 | Labor | 314938 | FALSE | FALSE | 0 | 350154.7 | -35216.7 | FALSE
P025 | Aspen Medical 25 | Labor | 591801.49 | FALSE | FALSE | 0 | 642821.22 | -51019.73 | FALSE
P032 | Granite Residences 32 | Labor | 467456.09 | FALSE | FALSE | 0 | 542262.73 | -74806.64 | FALSE
P040 | Summit Commons 40 | Labor | 329547.55 | FALSE | FALSE | 0 | 317255.69 | 12291.86 | FALSE
P064 | Juniper Commons 64 | Labor | 341951.76 | FALSE | FALSE | 0 | 362893.31 | -20941.55 | FALSE
P092 | Copper Retail 92 | Labor | 204531.46 | FALSE | FALSE | 0 | 196471.08 | 8060.38 | FALSE
P014 | Bonneville Lodge 14 | Labor | 536404 | FALSE | FALSE | 0 | 556199.55 | -19795.55 | FALSE
P015 | Juniper Residences 15 | Labor | 290227.7 | FALSE | FALSE | 0 | 306820.52 | -16592.82 | FALSE
P030 | Granite Center 30 | Labor | 561215.4 | FALSE | FALSE | 0 | 593538.51 | -32323.11 | FALSE
P037 | Wasatch Medical 37 | Labor | 249165.64 | FALSE | FALSE | 0 | 267322.68 | -18157.04 | FALSE
P067 | Copper Office 67 | Labor | 149138.24 | FALSE | FALSE | 0 | 149545.06 | -406.82 | FALSE
P069 | Bonneville Retail 69 | Labor | 169037.14 | FALSE | FALSE | 0 | 191439.83 | -22402.69 | FALSE
P096 | Granite Center 96 | Labor | 485562 | FALSE | FALSE | 0 | 159953.83 | 325608.17 | FALSE
P010 | Juniper Office 10 | Labor | 148883.21 | FALSE | FALSE | 0 | 150667.64 | -1784.43 | FALSE
P052 | Summit Medical 52 | Labor | 508941.41 | FALSE | FALSE | 0 | 571142.27 | -62200.86 | FALSE
P089 | Aspen Center 89 | Labor | 254462 | FALSE | FALSE | 0 | 36686.09 | 217775.91 | FALSE
P024 | Aspen Retail 24 | Labor | 323234.71 | FALSE | FALSE | 0 | 362642.98 | -39408.27 | FALSE
P070 | Granite Commons 70 | Labor | 276982.83 | FALSE | FALSE | 0 | 304353.6 | -27370.77 | FALSE
P072 | Aspen Office 72 | Labor | 239292.3 | FALSE | FALSE | 0 | 281570.87 | -42278.57 | FALSE
P073 | Canyon Commons 73 | Labor | 490438 | FALSE | FALSE | 0 | 580916.08 | -90478.08 | FALSE
P086 | Copper Center 86 | Labor | 108513 | FALSE | FALSE | 0 | 70550.45 | 37962.55 | FALSE
P005 | Summit Residences 05 | Labor | 556938.93 | FALSE | FALSE | 0 | 645998.01 | -89059.08 | FALSE
P017 | Summit Retail 17 | Labor | 389586 | FALSE | FALSE | 0 | 457801.9 | -68215.9 | FALSE
P022 | Juniper Medical 22 | Labor | 779495.08 | FALSE | FALSE | 0 | 858693.32 | -79198.24 | FALSE
P057 | Juniper Commons 57 | Labor | 213786 | FALSE | FALSE | 0 | 225545.13 | -11759.13 | FALSE
P059 | Aspen Residences 59 | Labor | 140535 | FALSE | FALSE | 0 | 157090.74 | -16555.74 | FALSE
P060 | Canyon Retail 60 | Labor | 364775.04 | FALSE | FALSE | 0 | 366192.48 | -1417.44 | FALSE
P079 | Canyon Center 79 | Labor | 319200 | FALSE | FALSE | 0 | 295304.65 | 23895.35 | FALSE
P019 | Wasatch Center 19 | Labor | 130838.79 | FALSE | FALSE | 0 | 155047.27 | -24208.48 | FALSE
P027 | Canyon Renovation 27 | Labor | 443408.07 | FALSE | FALSE | 0 | 479067.5 | -35659.43 | FALSE
P042 | Juniper Residences 42 | Labor | 522102.34 | FALSE | FALSE | 0 | 596100.48 | -73998.14 | FALSE
P045 | Bonneville Office 45 | Labor | 317520 | FALSE | FALSE | 0 | 304708.87 | 12811.13 | FALSE
P053 | Wasatch Center 53 | Labor | 379995 | FALSE | FALSE | 0 | 417968.14 | -37973.14 | FALSE
P085 | Summit Residences 85 | Labor | 234452.75 | FALSE | FALSE | 0 | 233519.19 | 933.56 | FALSE
P088 | Copper Center 88 | Labor | 175942.45 | FALSE | FALSE | 0 | 141221.51 | 34720.94 | FALSE
P002 | Wasatch Renovation 02 | Labor | 179172 | FALSE | FALSE | 0 | 183203.76 | -4031.76 | FALSE
P021 | Copper Center 21 | Labor | 637511.16 | FALSE | FALSE | 0 | 753709.84 | -116198.68 | FALSE
P036 | Bonneville Commons 36 | Labor | 531950 | FALSE | FALSE | 0 | 545334.46 | -13384.46 | FALSE
P062 | Granite Residences 62 | Labor | 566632.78 | FALSE | FALSE | 0 | 628634.22 | -62001.44 | FALSE
P081 | Canyon Center 81 | Labor | 189125 | FALSE | FALSE | 0 | 145105.79 | 44019.21 | FALSE
P082 | Wasatch Retail 82 | Labor | 477800.95 | FALSE | FALSE | 0 | 468362.39 | 9438.56 | FALSE
P001 | Juniper Retail 01 | Materials | 369577.78 | FALSE | FALSE | 13385.62 | 375450.91 | -5873.13 | FALSE
P002 | Wasatch Renovation 02 | Subcontractors | 185808 | FALSE | FALSE | 14006.84 | 173772.01 | 12035.99 | FALSE
P006 | Granite Commons 06 | Equipment | 64285 | FALSE | FALSE | 1526.27 | 64269.93 | 15.07 | FALSE
P006 | Granite Commons 06 | General Conditions | 102856 | FALSE | FALSE | 13667.77 | 90618.77 | 12237.23 | FALSE
P008 | Bonneville Renovation 08 | Other | 46380 | FALSE | FALSE | 2062.96 | 43399.62 | 2980.38 | FALSE
P010 | Juniper Office 10 | Other | 17149.81 | FALSE | FALSE | 2158.18 | 13136.5 | 4013.31 | FALSE
P018 | Wasatch Renovation 18 | Equipment | 60565 | FALSE | FALSE | 2630.75 | 64006.58 | -3441.58 | FALSE
P023 | Summit Office 23 | Subcontractors | 689229 | FALSE | FALSE | 0 | 764221.38 | -74992.38 | FALSE
P025 | Aspen Medical 25 | Materials | 659881.88 | FALSE | FALSE | 54861.88 | 659111.01 | 770.87 | FALSE
P034 | Bonneville Office 34 | Equipment | 26870 | FALSE | FALSE | 3700.33 | 25596.97 | 1273.03 | FALSE
P034 | Bonneville Office 34 | General Conditions | 42992 | FALSE | FALSE | 6100.22 | 41622.8 | 1369.2 | FALSE
P047 | Granite Lodge 47 | Permits & Fees | 135684 | FALSE | FALSE | 17458.84 | 128992.74 | 6691.26 | FALSE
P048 | Bonneville Office 48 | Other | 15409.36 | FALSE | FALSE | 2622.82 | 13797.72 | 1611.64 | FALSE
P058 | Bonneville Medical 58 | Other | 11883 | FALSE | FALSE | 533.66 | 10108.86 | 1774.14 | FALSE
P059 | Aspen Residences 59 | Materials | 130125 | FALSE | FALSE | 15755.72 | 128748.02 | 1376.98 | FALSE
P063 | Summit Office 63 | Materials | 270835.49 | FALSE | FALSE | 34567.98 | 265370.95 | 5464.54 | FALSE
P066 | Canyon Medical 66 | Permits & Fees | 23576.37 | FALSE | FALSE | 1477.41 | 21058.65 | 2517.72 | FALSE
P074 | Copper Center 74 | Other | 38985 | FALSE | FALSE | 0 | 35210.96 | 3774.04 | FALSE
P075 | Granite Lodge 75 | Permits & Fees | 62598 | FALSE | FALSE | 3690.13 | 58068.94 | 4529.06 | FALSE
P081 | Canyon Center 81 | Other | 22695 | FALSE | FALSE | 1214.16 | 14234.4 | 8460.6 | FALSE
P082 | Wasatch Retail 82 | Permits & Fees | 45740.58 | FALSE | FALSE | 9848.14 | 34899.51 | 10841.07 | FALSE
P084 | Bonneville Renovation 84 | Subcontractors | 247725 | FALSE | FALSE | 0 | 222897.84 | 24827.16 | FALSE
P089 | Aspen Center 89 | Other | 29361 | FALSE | FALSE | 261.74 | 3899.47 | 25461.53 | FALSE
P091 | Granite Medical 91 | Permits & Fees | 71916.17 | FALSE | FALSE | 8250.99 | 55479.07 | 16437.1 | FALSE
P095 | Summit Lodge 95 | Equipment | 21200 | FALSE | FALSE | 871.8 | 16793.1 | 4406.9 | FALSE
P009 | Wasatch Retail 09 | Subcontractors | 155008 | FALSE | FALSE | 13436.01 | 150642.93 | 4365.07 | FALSE
P018 | Wasatch Renovation 18 | General Conditions | 84791 | FALSE | FALSE | 7663.28 | 90736.8 | -5945.8 | FALSE
P022 | Juniper Medical 22 | Other | 88963.46 | FALSE | FALSE | 5005.25 | 76164.45 | 12799.01 | FALSE
P032 | Granite Residences 32 | Other | 54176.8 | FALSE | FALSE | 0 | 63416.31 | -9239.51 | FALSE
P038 | Canyon Renovation 38 | Materials | 161674.07 | FALSE | FALSE | 15371.62 | 156996.4 | 4677.67 | FALSE
P083 | Wasatch Renovation 83 | Permits & Fees | 44600 | FALSE | FALSE | 5262.8 | 38177.81 | 6422.19 | FALSE
P095 | Summit Lodge 95 | General Conditions | 47700 | FALSE | FALSE | 2734.79 | 34800.16 | 12899.84 | FALSE
P096 | Granite Center 96 | Permits & Fees | 132426 | FALSE | FALSE | 3088.15 | 43262.31 | 89163.69 | FALSE
P019 | Wasatch Center 19 | Materials | 135661.01 | FALSE | FALSE | 11762.77 | 138147.34 | -2486.33 | FALSE
P078 | Aspen Residences 78 | Other | 37096 | FALSE | FALSE | 1143.46 | 28883.22 | 8212.78 | FALSE
P040 | Summit Commons 40 | Other | 31676.55 | FALSE | FALSE | 0 | 29833.95 | 1842.6 | FALSE
P002 | Wasatch Renovation 02 | Other | 19908 | FALSE | FALSE | 1750.12 | 19877.08 | 30.92 | FALSE
P008 | Bonneville Renovation 08 | Subcontractors | 718890 | FALSE | FALSE | 45225.05 | 694202.76 | 24687.24 | FALSE
P009 | Wasatch Retail 09 | Other | 16608 | FALSE | FALSE | 2956.33 | 15429.07 | 1178.93 | FALSE
P012 | Canyon Retail 12 | Equipment | 44369.93 | FALSE | FALSE | 5947.43 | 38229.7 | 6140.23 | FALSE
P019 | Wasatch Center 19 | Permits & Fees | 12426.81 | FALSE | FALSE | 504.62 | 11782.88 | 643.93 | FALSE
P022 | Juniper Medical 22 | Subcontractors | 807211.62 | FALSE | FALSE | 136169.43 | 666404.43 | 140807.19 | FALSE
P023 | Summit Office 23 | Other | 76581 | FALSE | FALSE | 9534.95 | 74516.8 | 2064.2 | FALSE
P030 | Granite Center 30 | Equipment | 69985.04 | FALSE | FALSE | 5717.56 | 66615.91 | 3369.13 | FALSE
P030 | Granite Center 30 | General Conditions | 121655.07 | FALSE | FALSE | 26867.59 | 109025.89 | 12629.18 | FALSE
P032 | Granite Residences 32 | Subcontractors | 568034.29 | FALSE | FALSE | 19529.38 | 621795.15 | -53760.86 | FALSE
P038 | Canyon Renovation 38 | Permits & Fees | 25417 | FALSE | FALSE | 727.03 | 24768.84 | 648.16 | FALSE
P039 | Granite Commons 39 | Equipment | 23236 | FALSE | FALSE | 1024.72 | 23824.24 | -588.24 | FALSE
P039 | Granite Commons 39 | General Conditions | 52281 | FALSE | FALSE | 0 | 56328.54 | -4047.54 | FALSE
P040 | Summit Commons 40 | Subcontractors | 214823 | FALSE | FALSE | 5121.84 | 207462.63 | 7360.37 | FALSE
P047 | Granite Lodge 47 | Materials | 633192 | FALSE | FALSE | 61713.22 | 612021.28 | 21170.72 | FALSE
P048 | Bonneville Office 48 | Subcontractors | 146301.34 | FALSE | FALSE | 2896.64 | 146220.88 | 80.46 | FALSE
P063 | Summit Office 63 | Permits & Fees | 42993.84 | FALSE | FALSE | 1346.79 | 45650.3 | -2656.46 | FALSE
P066 | Canyon Medical 66 | Materials | 149968.96 | FALSE | FALSE | 17905.89 | 127888.76 | 22080.2 | FALSE
P075 | Granite Lodge 75 | Materials | 605114 | FALSE | FALSE | 20443.87 | 591039.99 | 14074.01 | FALSE
P077 | Canyon Residences 77 | Equipment | 45200.38 | FALSE | FALSE | 5550.3 | 32122.24 | 13078.14 | FALSE
P077 | Canyon Residences 77 | General Conditions | 72285.29 | FALSE | FALSE | 1530.01 | 64309.47 | 7975.82 | FALSE
P081 | Canyon Center 81 | Subcontractors | 234515 | FALSE | FALSE | 23520.02 | 147878.89 | 86636.11 | FALSE
P082 | Wasatch Retail 82 | Materials | 494489.32 | FALSE | FALSE | 34433.8 | 474872.8 | 19616.52 | FALSE
P083 | Wasatch Renovation 83 | Materials | 267600 | FALSE | FALSE | 0 | 287455.3 | -19855.3 | FALSE
P084 | Bonneville Renovation 84 | Other | 27525 | FALSE | FALSE | 4412.94 | 18745.92 | 8779.08 | FALSE
P087 | Copper Office 87 | Equipment | 116598.88 | FALSE | FALSE | 6801.87 | 48226.48 | 68372.4 | FALSE
P087 | Copper Office 87 | General Conditions | 163426.13 | FALSE | FALSE | 4505.74 | 74254.66 | 89171.47 | FALSE
P089 | Aspen Center 89 | Subcontractors | 264249 | FALSE | FALSE | 1294.51 | 33539.79 | 230709.21 | FALSE
P096 | Granite Center 96 | Materials | 617988 | FALSE | FALSE | 31195.44 | 183989.38 | 433998.62 | FALSE
P001 | Juniper Retail 01 | Permits & Fees | 34467.61 | FALSE | FALSE | 1969.33 | 33646.88 | 820.73 | FALSE
P010 | Juniper Office 10 | Subcontractors | 180279.4 | FALSE | FALSE | 12179.16 | 163201.12 | 17078.28 | FALSE
P012 | Canyon Retail 12 | General Conditions | 77359.22 | FALSE | FALSE | 15534.2 | 63104.04 | 14255.18 | FALSE
P025 | Aspen Medical 25 | Permits & Fees | 67489.93 | FALSE | FALSE | 6809.44 | 59907.19 | 7582.74 | FALSE
P058 | Bonneville Medical 58 | Subcontractors | 110908 | FALSE | FALSE | 5461.75 | 108000.17 | 2907.83 | FALSE
P059 | Aspen Residences 59 | Permits & Fees | 20820 | FALSE | FALSE | 0 | 21391.36 | -571.36 | FALSE
P074 | Copper Center 74 | Subcontractors | 402845 | FALSE | FALSE | 26573.99 | 392363.42 | 10481.58 | FALSE
P078 | Aspen Residences 78 | Subcontractors | 336149.85 | FALSE | FALSE | 0 | 298652.22 | 37497.63 | FALSE
P091 | Granite Medical 91 | Materials | 452458.67 | FALSE | FALSE | 33821.27 | 370192.39 | 82266.28 | FALSE
P001 | Juniper Retail 01 | Other | 34467.61 | FALSE | FALSE | 1459.65 | 32763.71 | 1703.9 | FALSE
P009 | Wasatch Retail 09 | Permits & Fees | 22144 | FALSE | FALSE | 3131.42 | 21171.92 | 972.08 | FALSE
P010 | Juniper Office 10 | Materials | 144940.92 | FALSE | FALSE | 0 | 137585.37 | 7355.55 | FALSE
P014 | Bonneville Lodge 14 | Equipment | 97528 | FALSE | FALSE | 12818.05 | 88409.87 | 9118.13 | FALSE
P014 | Bonneville Lodge 14 | General Conditions | 170674 | FALSE | FALSE | 7985.92 | 169922.71 | 751.29 | FALSE
P017 | Summit Retail 17 | Equipment | 49801.79 | FALSE | FALSE | 4810.35 | 47295.31 | 2506.48 | FALSE
P017 | Summit Retail 17 | General Conditions | 86995.66 | FALSE | FALSE | 23406.52 | 73574.2 | 13421.46 | FALSE
P019 | Wasatch Center 19 | Other | 12426.81 | FALSE | FALSE | 1782.95 | 11606.08 | 820.73 | FALSE
P022 | Juniper Medical 22 | Materials | 869185.26 | FALSE | FALSE | 110677.39 | 829350.31 | 39834.95 | FALSE
P025 | Aspen Medical 25 | Other | 67489.92 | FALSE | FALSE | 5498.07 | 65721.55 | 1768.37 | FALSE
P038 | Canyon Renovation 38 | Other | 19135.01 | FALSE | FALSE | 1523.7 | 19742.61 | -607.6 | FALSE
P046 | Granite Lodge 46 | General Conditions | 78635.19 | FALSE | FALSE | 24310.39 | 64264.85 | 14370.34 | FALSE
P047 | Granite Lodge 47 | Subcontractors | 701034 | FALSE | FALSE | 0 | 707071.92 | -6037.92 | FALSE
P058 | Bonneville Medical 58 | Materials | 99025 | FALSE | FALSE | 5399.31 | 97550.71 | 1474.29 | FALSE
P063 | Summit Office 63 | Other | 32299.85 | FALSE | FALSE | 1409.78 | 36040.51 | -3740.66 | FALSE
P066 | Canyon Medical 66 | Subcontractors | 166779.03 | FALSE | FALSE | 10131.48 | 149433.24 | 17345.79 | FALSE
P074 | Copper Center 74 | Materials | 311880 | FALSE | FALSE | 23897.91 | 283924.19 | 27955.81 | FALSE
P075 | Granite Lodge 75 | Subcontractors | 563382 | FALSE | FALSE | 25478.15 | 518992.41 | 44389.59 | FALSE
P078 | Aspen Residences 78 | Materials | 361811.82 | FALSE | FALSE | 27303.96 | 291476.84 | 70334.98 | FALSE
P081 | Canyon Center 81 | Materials | 181560 | FALSE | FALSE | 8404.75 | 130904.53 | 50655.47 | FALSE
P083 | Wasatch Renovation 83 | Subcontractors | 345650 | FALSE | FALSE | 0 | 351849.86 | -6199.86 | FALSE
P089 | Aspen Center 89 | Materials | 283823 | FALSE | FALSE | 4177.55 | 34870.02 | 248952.98 | FALSE
P091 | Granite Medical 91 | Subcontractors | 569403.25 | FALSE | FALSE | 15508.9 | 510519.76 | 58883.49 | FALSE
P096 | Granite Center 96 | Subcontractors | 684201 | FALSE | FALSE | 16292.51 | 194927.93 | 489273.07 | FALSE
P002 | Wasatch Renovation 02 | Permits & Fees | 26544 | FALSE | FALSE | 3009.81 | 24516.59 | 2027.41 | FALSE
P032 | Granite Residences 32 | Materials | 454148.79 | FALSE | FALSE | 53256.69 | 486503.19 | -32354.4 | FALSE
P040 | Summit Commons 40 | Materials | 340728.89 | FALSE | FALSE | 24666.05 | 320374.43 | 20354.46 | FALSE
P046 | Granite Lodge 46 | Equipment | 48999.51 | FALSE | FALSE | 5139.74 | 43789.27 | 5210.24 | FALSE
P048 | Bonneville Office 48 | Materials | 132975.74 | FALSE | FALSE | 7807.63 | 142073.66 | -9097.92 | FALSE
P082 | Wasatch Retail 82 | Subcontractors | 313380.37 | FALSE | FALSE | 17181.53 | 290170.9 | 23209.47 | FALSE
P084 | Bonneville Renovation 84 | Permits & Fees | 27525 | FALSE | FALSE | 1888.72 | 21769.75 | 5755.25 | FALSE
P023 | Summit Office 23 | Permits & Fees | 76581 | FALSE | FALSE | 2170.41 | 83243.09 | -6662.09 | FALSE
P008 | Bonneville Renovation 08 | Materials | 649320 | FALSE | FALSE | 62632.67 | 659200.04 | -9880.04 | FALSE
P059 | Aspen Residences 59 | Other | 15615 | FALSE | FALSE | 0 | 17734.68 | -2119.68 | FALSE
P001 | Juniper Retail 01 | Subcontractors | 232248.25 | FALSE | FALSE | 0 | 232027.57 | 220.68 | FALSE
P003 | Summit Center 03 | Equipment | 59808.11 | FALSE | FALSE | 2058.58 | 51385.69 | 8422.42 | FALSE
P003 | Summit Center 03 | General Conditions | 104525.85 | FALSE | FALSE | 11417.55 | 92987.91 | 11537.94 | FALSE
P008 | Bonneville Renovation 08 | Permits & Fees | 139140 | FALSE | FALSE | 10714.68 | 138860.19 | 279.81 | FALSE
P022 | Juniper Medical 22 | Permits & Fees | 88963.45 | FALSE | FALSE | 10740.7 | 77082.48 | 11880.97 | FALSE
P023 | Summit Office 23 | Materials | 740283 | FALSE | FALSE | 124570.46 | 688453.53 | 51829.47 | FALSE
P027 | Canyon Renovation 27 | Equipment | 87341.18 | FALSE | FALSE | 18990.48 | 69042.06 | 18299.12 | FALSE
P027 | Canyon Renovation 27 | General Conditions | 139841.63 | FALSE | FALSE | 21518.46 | 129267.48 | 10574.15 | FALSE
P032 | Granite Residences 32 | Permits & Fees | 71371.8 | FALSE | FALSE | 7867.14 | 67139.04 | 4232.76 | FALSE
P037 | Wasatch Medical 37 | General Conditions | 79188.32 | FALSE | FALSE | 4259.08 | 80505.61 | -1317.29 | FALSE
P038 | Canyon Renovation 38 | Subcontractors | 179797.56 | FALSE | FALSE | 0 | 194605.31 | -14807.75 | FALSE
P040 | Summit Commons 40 | Permits & Fees | 31676.56 | FALSE | FALSE | 4788.25 | 26156.96 | 5519.6 | FALSE
P047 | Granite Lodge 47 | Other | 45228 | FALSE | FALSE | 8337 | 37952.11 | 7275.89 | FALSE
P054 | Granite Office 54 | Equipment | 16625.14 | FALSE | FALSE | 0 | 15078.63 | 1546.51 | FALSE
P054 | Granite Office 54 | General Conditions | 29074.57 | FALSE | FALSE | 1363.04 | 27546.3 | 1528.27 | FALSE
P059 | Aspen Residences 59 | Subcontractors | 145740 | FALSE | FALSE | 19271.72 | 136883.06 | 8856.94 | FALSE
P063 | Summit Office 63 | Subcontractors | 302372.88 | FALSE | FALSE | 35078.83 | 297838.21 | 4534.67 | FALSE
P070 | Granite Commons 70 | Equipment | 49429.26 | FALSE | FALSE | 6426.49 | 44767.66 | 4661.6 | FALSE
P071 | Wasatch Office 71 | Equipment | 26134.69 | FALSE | FALSE | 1787.43 | 25286.24 | 848.45 | FALSE
P071 | Wasatch Office 71 | General Conditions | 45681.15 | FALSE | FALSE | 3689.46 | 45364.84 | 316.31 | FALSE
P075 | Granite Lodge 75 | Other | 62598 | FALSE | FALSE | 5101.38 | 60931.54 | 1666.46 | FALSE
P080 | Aspen Lodge 80 | General Conditions | 39294 | FALSE | FALSE | 1165.34 | 31974.61 | 7319.39 | FALSE
P081 | Canyon Center 81 | Permits & Fees | 30260 | FALSE | FALSE | 2641.86 | 19518.25 | 10741.75 | FALSE
P082 | Wasatch Retail 82 | Other | 45740.59 | FALSE | FALSE | 0 | 39569.79 | 6170.8 | FALSE
P083 | Wasatch Renovation 83 | Other | 33450 | FALSE | FALSE | 3284.05 | 30718.24 | 2731.76 | FALSE
P085 | Summit Residences 85 | Equipment | 44753.42 | FALSE | FALSE | 1142.47 | 40787.99 | 3965.43 | FALSE
P089 | Aspen Center 89 | Permits & Fees | 29361 | FALSE | FALSE | 329.09 | 3576.67 | 25784.33 | FALSE
P091 | Granite Medical 91 | Other | 54461.15 | FALSE | FALSE | 7681.32 | 41570.58 | 12890.57 | FALSE
P096 | Granite Center 96 | Other | 44142 | FALSE | FALSE | 2701.22 | 12267.02 | 31874.98 | FALSE
P002 | Wasatch Renovation 02 | Materials | 165900 | FALSE | FALSE | 11284.34 | 156686.28 | 9213.72 | FALSE
P009 | Wasatch Retail 09 | Materials | 138400 | FALSE | FALSE | 11806.81 | 147878.7 | -9478.7 | FALSE
P010 | Juniper Office 10 | Permits & Fees | 22543.81 | FALSE | FALSE | 1685.05 | 19431.5 | 3112.31 | FALSE
P019 | Wasatch Center 19 | Subcontractors | 86827.98 | FALSE | FALSE | 14880.03 | 79992.03 | 6835.95 | FALSE
P037 | Wasatch Medical 37 | Equipment | 49476.79 | FALSE | FALSE | 0 | 49880.99 | -404.2 | FALSE
P050 | Granite Lodge 50 | General Conditions | 96633.75 | FALSE | FALSE | 6885.29 | 102078.96 | -5445.21 | FALSE
P058 | Bonneville Medical 58 | Permits & Fees | 15844 | FALSE | FALSE | 900.42 | 14897.26 | 946.74 | FALSE
P066 | Canyon Medical 66 | Other | 17749.38 | FALSE | FALSE | 1630.74 | 13942.13 | 3807.25 | FALSE
P084 | Bonneville Renovation 84 | Materials | 266075 | FALSE | FALSE | 65624.72 | 176400.77 | 89674.23 | FALSE
P025 | Aspen Medical 25 | Subcontractors | 612723.56 | FALSE | FALSE | 113418.61 | 505562.83 | 107160.73 | FALSE
P050 | Granite Lodge 50 | Equipment | 43036.65 | FALSE | FALSE | 5162.9 | 40075.87 | 2960.78 | FALSE
P070 | Granite Commons 70 | General Conditions | 86398.76 | FALSE | FALSE | 7211.57 | 84390.61 | 2008.15 | FALSE
P074 | Copper Center 74 | Permits & Fees | 51980 | FALSE | FALSE | 4067.15 | 45168.01 | 6811.99 | FALSE
P078 | Aspen Residences 78 | Permits & Fees | 37095.99 | FALSE | FALSE | 3792.33 | 26725.41 | 10370.58 | FALSE
P080 | Aspen Lodge 80 | Equipment | 17464 | FALSE | FALSE | 305.19 | 14052.41 | 3411.59 | FALSE
P085 | Summit Residences 85 | General Conditions | 62758.37 | FALSE | FALSE | 4149.37 | 53701.73 | 9056.64 | FALSE
P048 | Bonneville Office 48 | Permits & Fees | 20347.36 | FALSE | FALSE | 1217.8 | 20286.63 | 60.73 | FALSE
P003 | Summit Center 03 | Materials | 424743.83 | FALSE | FALSE | 0 | 429233.55 | -4489.72 | FALSE
P009 | Wasatch Retail 09 | Equipment | 22144 | FALSE | FALSE | 1745.12 | 22309.62 | -165.62 | FALSE
P018 | Wasatch Renovation 18 | Subcontractors | 327051 | FALSE | FALSE | 38033.91 | 315650.02 | 11400.98 | FALSE
P023 | Summit Office 23 | Equipment | 127635 | FALSE | FALSE | 0 | 135081.85 | -7446.85 | FALSE
P023 | Summit Office 23 | General Conditions | 178689 | FALSE | FALSE | 8418.04 | 205684.31 | -26995.31 | FALSE
P037 | Wasatch Medical 37 | Materials | 239728.43 | FALSE | FALSE | 56924.03 | 194453.06 | 45275.37 | FALSE
P039 | Granite Commons 39 | Other | 17427 | FALSE | FALSE | 1950.36 | 15218.34 | 2208.66 | FALSE
P046 | Granite Lodge 46 | Permits & Fees | 38727.67 | FALSE | FALSE | 6013.93 | 35052.82 | 3674.85 | FALSE
P054 | Granite Office 54 | Materials | 133622.82 | FALSE | FALSE | 0 | 132470.73 | 1152.09 | FALSE
P070 | Granite Commons 70 | Materials | 350512.09 | FALSE | FALSE | 19256.89 | 391861.81 | -41349.72 | FALSE
P071 | Wasatch Office 71 | Materials | 185343.37 | FALSE | FALSE | 20725.62 | 186683.22 | -1339.85 | FALSE
P077 | Canyon Residences 77 | Other | 27084.91 | FALSE | FALSE | 6430.68 | 16636.62 | 10448.29 | FALSE
P084 | Bonneville Renovation 84 | Equipment | 45875 | FALSE | FALSE | 2482.75 | 36343.14 | 9531.86 | FALSE
P084 | Bonneville Renovation 84 | General Conditions | 64225 | FALSE | FALSE | 7250.69 | 50161.94 | 14063.06 | FALSE
P087 | Copper Office 87 | Other | 70006.26 | FALSE | FALSE | 7391.54 | 27636.05 | 42370.21 | FALSE
P002 | Wasatch Renovation 02 | Equipment | 26544 | FALSE | FALSE | 522.13 | 27193.18 | -649.18 | FALSE
P002 | Wasatch Renovation 02 | General Conditions | 59724 | FALSE | FALSE | 6081.04 | 52990.27 | 6733.73 | FALSE
P006 | Granite Commons 06 | Subcontractors | 398567 | FALSE | FALSE | 26990.98 | 389700.22 | 8866.78 | FALSE
P009 | Wasatch Retail 09 | General Conditions | 49824 | FALSE | FALSE | 7280.8 | 49731.82 | 92.18 | FALSE
P012 | Canyon Retail 12 | Other | 22761.3 | FALSE | FALSE | 2481.33 | 18069.62 | 4691.68 | FALSE
P014 | Bonneville Lodge 14 | Permits & Fees | 146292 | FALSE | FALSE | 0 | 164317.2 | -18025.2 | FALSE
P027 | Canyon Renovation 27 | Materials | 427663.25 | FALSE | FALSE | 75493.35 | 400926.26 | 26736.99 | FALSE
P030 | Granite Center 30 | Other | 51670.02 | FALSE | FALSE | 0 | 56610.1 | -4940.08 | FALSE
P034 | Bonneville Office 34 | Subcontractors | 166594 | FALSE | FALSE | 28374.22 | 151463.08 | 15130.92 | FALSE
P050 | Granite Lodge 50 | Materials | 270483.57 | FALSE | FALSE | 14696.2 | 290963.68 | -20480.11 | FALSE
P080 | Aspen Lodge 80 | Materials | 109150 | FALSE | FALSE | 13046.6 | 76654.26 | 32495.74 | FALSE
P085 | Summit Residences 85 | Materials | 261460.18 | FALSE | FALSE | 9935.39 | 243780.23 | 17679.95 | FALSE
P095 | Summit Lodge 95 | Subcontractors | 148400 | FALSE | FALSE | 24306.81 | 93468.33 | 54931.67 | FALSE
P017 | Summit Retail 17 | Permits & Fees | 37193.86 | FALSE | FALSE | 6201.6 | 30987.73 | 6206.13 | FALSE
P003 | Summit Center 03 | Permits & Fees | 88328.74 | FALSE | FALSE | 12702.38 | 77720.69 | 10608.05 | FALSE
P006 | Granite Commons 06 | Other | 38571 | FALSE | FALSE | 1176.57 | 41091.43 | -2520.43 | FALSE
P008 | Bonneville Renovation 08 | Equipment | 92760 | FALSE | FALSE | 0 | 91869.58 | 890.42 | FALSE
P008 | Bonneville Renovation 08 | General Conditions | 162330 | FALSE | FALSE | 13476.13 | 148756.59 | 13573.41 | FALSE
P012 | Canyon Retail 12 | Subcontractors | 348189.4 | FALSE | FALSE | 71929.7 | 291763.27 | 56426.13 | FALSE
P018 | Wasatch Renovation 18 | Other | 36339 | FALSE | FALSE | 5498.44 | 35530.55 | 808.45 | FALSE
P022 | Juniper Medical 22 | Equipment | 148030.18 | FALSE | FALSE | 16648.87 | 125974 | 22056.18 | FALSE
P022 | Juniper Medical 22 | General Conditions | 207823.63 | FALSE | FALSE | 28962.89 | 189178.61 | 18645.02 | FALSE
P027 | Canyon Renovation 27 | Permits & Fees | 69681.45 | FALSE | FALSE | 11018.63 | 64702.02 | 4979.43 | FALSE
P032 | Granite Residences 32 | Equipment | 89862.7 | FALSE | FALSE | 0 | 99374.4 | -9511.7 | FALSE
P032 | Granite Residences 32 | General Conditions | 144039.5 | FALSE | FALSE | 16713.41 | 152853.01 | -8813.51 | FALSE
P034 | Bonneville Office 34 | Other | 16122 | FALSE | FALSE | 1990.94 | 17221.85 | -1099.85 | FALSE
P037 | Wasatch Medical 37 | Permits & Fees | 39530.53 | FALSE | FALSE | 5532.02 | 36141.26 | 3389.27 | FALSE
P039 | Granite Commons 39 | Subcontractors | 162652 | FALSE | FALSE | 4371.57 | 166982.84 | -4330.84 | FALSE
P040 | Summit Commons 40 | Equipment | 42324.33 | FALSE | FALSE | 9514.21 | 30692.57 | 11631.76 | FALSE
P040 | Summit Commons 40 | General Conditions | 74000.89 | FALSE | FALSE | 5413.24 | 67738.29 | 6262.6 | FALSE
P046 | Granite Lodge 46 | Materials | 255962.8 | FALSE | FALSE | 0 | 282902.93 | -26940.13 | FALSE
P048 | Bonneville Office 48 | Equipment | 20645.04 | FALSE | FALSE | 2596.61 | 19105.83 | 1539.21 | FALSE
P050 | Granite Lodge 50 | Permits & Fees | 42923.1 | FALSE | FALSE | 2044.63 | 44517.16 | -1594.06 | FALSE
P054 | Granite Office 54 | Permits & Fees | 12449.43 | FALSE | FALSE | 569.69 | 11540.71 | 908.72 | FALSE
P058 | Bonneville Medical 58 | Equipment | 15844 | FALSE | FALSE | 3203.01 | 12959.31 | 2884.69 | FALSE
P071 | Wasatch Office 71 | Permits & Fees | 38656.46 | FALSE | FALSE | 2488.74 | 41015.18 | -2358.72 | FALSE
P074 | Copper Center 74 | Equipment | 64975 | FALSE | FALSE | 7916.61 | 53356.61 | 11618.39 | FALSE
P074 | Copper Center 74 | General Conditions | 103960 | FALSE | FALSE | 5100.8 | 99457.42 | 4502.58 | FALSE
P077 | Canyon Residences 77 | Subcontractors | 278759.38 | FALSE | FALSE | 43066.29 | 192104.36 | 86655.02 | FALSE
P078 | Aspen Residences 78 | Equipment | 61741.98 | FALSE | FALSE | 6438.69 | 43034.54 | 18707.44 | FALSE
P078 | Aspen Residences 78 | General Conditions | 86641.97 | FALSE | FALSE | 5953.69 | 68712.57 | 17929.4 | FALSE
P080 | Aspen Lodge 80 | Permits & Fees | 17464 | FALSE | FALSE | 357.02 | 13103.41 | 4360.59 | FALSE
P081 | Canyon Center 81 | Equipment | 37825 | FALSE | FALSE | 2004.98 | 26297.43 | 11527.57 | FALSE
P081 | Canyon Center 81 | General Conditions | 60520 | FALSE | FALSE | 4201.82 | 44011.83 | 16508.17 | FALSE
P087 | Copper Office 87 | Subcontractors | 632167.91 | FALSE | FALSE | 24933.16 | 267844.26 | 364323.65 | FALSE
P089 | Aspen Center 89 | Equipment | 48935 | FALSE | FALSE | 1101.88 | 5032.15 | 43902.85 | FALSE
P095 | Summit Lodge 95 | Other | 15900 | FALSE | FALSE | 917.33 | 11719.51 | 4180.49 | FALSE
P010 | Juniper Office 10 | Equipment | 28421.71 | FALSE | FALSE | 2760.53 | 23762.43 | 4659.28 | FALSE
P010 | Juniper Office 10 | General Conditions | 45571.52 | FALSE | FALSE | 3490.81 | 38787.99 | 6783.53 | FALSE
P014 | Bonneville Lodge 14 | Materials | 682696 | FALSE | FALSE | 56529.18 | 699624.33 | -16928.33 | FALSE
P017 | Summit Retail 17 | Materials | 403453.8 | FALSE | FALSE | 50963.48 | 387180.73 | 16273.07 | FALSE
P048 | Bonneville Office 48 | General Conditions | 45930.4 | FALSE | FALSE | 13039.31 | 37634.54 | 8295.86 | FALSE
P085 | Summit Residences 85 | Permits & Fees | 26877.95 | FALSE | FALSE | 0 | 23078.72 | 3799.23 | FALSE
P089 | Aspen Center 89 | General Conditions | 68509 | FALSE | FALSE | 0 | 9621.82 | 58887.18 | FALSE
P030 | Granite Center 30 | Subcontractors | 389225.37 | FALSE | FALSE | 102645.06 | 301558.44 | 87666.93 | FALSE
P058 | Bonneville Medical 58 | General Conditions | 35649 | FALSE | FALSE | 1561.32 | 35047.79 | 601.21 | FALSE
P070 | Granite Commons 70 | Permits & Fees | 73119.51 | FALSE | FALSE | 10787.62 | 71897.54 | 1221.97 | FALSE
P003 | Summit Center 03 | Other | 30180.73 | FALSE | FALSE | 1258.88 | 24353.59 | 5827.14 | FALSE
P006 | Granite Commons 06 | Permits & Fees | 51428 | FALSE | FALSE | 7478.77 | 43386.75 | 8041.25 | FALSE
P014 | Bonneville Lodge 14 | Subcontractors | 755842 | FALSE | FALSE | 0 | 799822.39 | -43980.39 | FALSE
P017 | Summit Retail 17 | Subcontractors | 256568.14 | FALSE | FALSE | 10279.09 | 275669.43 | -19101.29 | FALSE
P018 | Wasatch Renovation 18 | Permits & Fees | 36339 | FALSE | FALSE | 2601.48 | 36138.02 | 200.98 | FALSE
P027 | Canyon Renovation 27 | Other | 52500.45 | FALSE | FALSE | 11463.04 | 41424.75 | 11075.7 | FALSE
P034 | Bonneville Office 34 | Permits & Fees | 21496 | FALSE | FALSE | 0 | 23956.31 | -2460.31 | FALSE
P039 | Granite Commons 39 | Materials | 145225 | FALSE | FALSE | 8517.28 | 146723.7 | -1498.7 | FALSE
P046 | Granite Lodge 46 | Subcontractors | 313707.61 | FALSE | FALSE | 53143.2 | 269140.65 | 44566.96 | FALSE
P066 | Canyon Medical 66 | Equipment | 23710.56 | FALSE | FALSE | 0 | 23554.88 | 155.68 | FALSE
P070 | Granite Commons 70 | Other | 24919.51 | FALSE | FALSE | 0 | 23979.4 | 940.11 | FALSE
P075 | Granite Lodge 75 | Equipment | 104330 | FALSE | FALSE | 0 | 97861.34 | 6468.66 | FALSE
P077 | Canyon Residences 77 | Materials | 213854.68 | FALSE | FALSE | 22844.81 | 165000.57 | 48854.11 | FALSE
P080 | Aspen Lodge 80 | Other | 13098 | FALSE | FALSE | 2295.9 | 7521.07 | 5576.93 | FALSE
P082 | Wasatch Retail 82 | General Conditions | 106933.96 | FALSE | FALSE | 8847.31 | 94270.75 | 12663.21 | FALSE
P083 | Wasatch Renovation 83 | Equipment | 55750 | FALSE | FALSE | 5050.19 | 51928.55 | 3821.45 | FALSE
P085 | Summit Residences 85 | Other | 26877.95 | FALSE | FALSE | 0 | 25668.28 | 1209.67 | FALSE
P087 | Copper Office 87 | Materials | 679699.04 | FALSE | FALSE | 23716.07 | 295577.51 | 384121.53 | FALSE
P091 | Granite Medical 91 | Equipment | 90419.25 | FALSE | FALSE | 11637.21 | 65616.98 | 24802.27 | FALSE
P091 | Granite Medical 91 | General Conditions | 144880.42 | FALSE | FALSE | 7457.96 | 129251.81 | 15628.61 | FALSE
P095 | Summit Lodge 95 | Permits & Fees | 21200 | FALSE | FALSE | 1746.98 | 15642.22 | 5557.78 | FALSE
P096 | Granite Center 96 | Equipment | 88284 | FALSE | FALSE | 0 | 26818.79 | 61465.21 | FALSE
P096 | Granite Center 96 | General Conditions | 154497 | FALSE | FALSE | 0 | 48328.33 | 106168.67 | FALSE
P047 | Granite Lodge 47 | General Conditions | 158298 | FALSE | FALSE | 24251.47 | 128851.88 | 29446.12 | FALSE
P050 | Granite Lodge 50 | Other | 32249.09 | FALSE | FALSE | 3616.54 | 28424.04 | 3825.05 | FALSE
P054 | Granite Office 54 | Other | 12449.41 | FALSE | FALSE | 1043.1 | 9979.39 | 2470.02 | FALSE
P066 | Canyon Medical 66 | General Conditions | 53113.93 | FALSE | FALSE | 3940.76 | 46627.39 | 6486.54 | FALSE
P071 | Wasatch Office 71 | Other | 13176.47 | FALSE | FALSE | 340.57 | 13085.94 | 90.53 | FALSE
P075 | Granite Lodge 75 | General Conditions | 146062 | FALSE | FALSE | 2372.44 | 150297.36 | -4235.36 | FALSE
P082 | Wasatch Retail 82 | Equipment | 61193.37 | FALSE | FALSE | 3552.79 | 55555.68 | 5637.69 | FALSE
P083 | Wasatch Renovation 83 | General Conditions | 89200 | FALSE | FALSE | 15297.33 | 80295.68 | 8904.32 | FALSE
P012 | Canyon Retail 12 | Materials | 323268.62 | FALSE | FALSE | 49545.58 | 317870.19 | 5398.43 | FALSE
P037 | Wasatch Medical 37 | Other | 29711.51 | FALSE | FALSE | 3550.53 | 28465.59 | 1245.92 | FALSE
P030 | Granite Center 30 | Materials | 586080.44 | FALSE | FALSE | 96621.19 | 527197.83 | 58882.61 | FALSE
P047 | Granite Lodge 47 | Equipment | 90456 | FALSE | FALSE | 23760.39 | 62560.03 | 27895.97 | FALSE
P001 | Juniper Retail 01 | Equipment | 46016.92 | FALSE | FALSE | 2081.75 | 42535.85 | 3481.07 | FALSE
P001 | Juniper Retail 01 | General Conditions | 80484.53 | FALSE | FALSE | 6100.52 | 80825.35 | -340.82 | FALSE
P006 | Granite Commons 06 | Materials | 308568 | FALSE | FALSE | 13877.97 | 300759.8 | 7808.2 | FALSE
P012 | Canyon Retail 12 | Permits & Fees | 63673.29 | FALSE | FALSE | 323.8 | 65610.81 | -1937.52 | FALSE
P014 | Bonneville Lodge 14 | Other | 48764 | FALSE | FALSE | 7474.08 | 46205.63 | 2558.37 | FALSE
P017 | Summit Retail 17 | Other | 37193.87 | FALSE | FALSE | 4856.53 | 36027.76 | 1166.11 | FALSE
P019 | Wasatch Center 19 | Equipment | 16666.22 | FALSE | FALSE | 924.39 | 16233.86 | 432.36 | FALSE
P019 | Wasatch Center 19 | General Conditions | 29093.03 | FALSE | FALSE | 4707.92 | 28550.74 | 542.29 | FALSE
P025 | Aspen Medical 25 | Equipment | 112286.4 | FALSE | FALSE | 18369.5 | 97000.67 | 15285.73 | FALSE
P025 | Aspen Medical 25 | General Conditions | 157673.33 | FALSE | FALSE | 18530.65 | 153410.19 | 4263.14 | FALSE
P030 | Granite Center 30 | Permits & Fees | 51670.03 | FALSE | FALSE | 0 | 54073.24 | -2403.21 | FALSE
P039 | Granite Commons 39 | Permits & Fees | 23236 | FALSE | FALSE | 2657.67 | 22239.78 | 996.22 | FALSE
P046 | Granite Lodge 46 | Other | 29635.68 | FALSE | FALSE | 2550.76 | 27236.99 | 2398.69 | FALSE
P050 | Granite Lodge 50 | Subcontractors | 301937.83 | FALSE | FALSE | 40609.42 | 281852.59 | 20085.24 | FALSE
P054 | Granite Office 54 | Subcontractors | 84058.25 | FALSE | FALSE | 0 | 78497.81 | 5560.44 | FALSE
P059 | Aspen Residences 59 | Equipment | 20820 | FALSE | FALSE | 4727.83 | 18345.8 | 2474.2 | FALSE
P059 | Aspen Residences 59 | General Conditions | 46845 | FALSE | FALSE | 0 | 51375.19 | -4530.19 | FALSE
P070 | Granite Commons 70 | Subcontractors | 384613.33 | FALSE | FALSE | 0 | 418100.02 | -33486.69 | FALSE
P071 | Wasatch Office 71 | Subcontractors | 203362.22 | FALSE | FALSE | 6718.61 | 206163.44 | -2801.22 | FALSE
P077 | Canyon Residences 77 | Permits & Fees | 36230.92 | FALSE | FALSE | 5437.53 | 26845.54 | 9385.38 | FALSE
P095 | Summit Lodge 95 | Materials | 132500 | FALSE | FALSE | 0 | 109063.37 | 23436.63 | FALSE
P003 | Summit Center 03 | Subcontractors | 465587.98 | FALSE | FALSE | 26507.74 | 424211.79 | 41376.19 | FALSE
P018 | Wasatch Renovation 18 | Materials | 351277 | FALSE | FALSE | 58598.43 | 340653.65 | 10623.35 | FALSE
P027 | Canyon Renovation 27 | Subcontractors | 545536.62 | FALSE | FALSE | 48134.94 | 550639.72 | -5103.1 | FALSE
P034 | Bonneville Office 34 | Materials | 128976 | FALSE | FALSE | 29704.13 | 107859.85 | 21116.15 | FALSE
P037 | Wasatch Medical 37 | Subcontractors | 307825.11 | FALSE | FALSE | 64768.61 | 272186.48 | 35638.63 | FALSE
P038 | Canyon Renovation 38 | Equipment | 25561.51 | FALSE | FALSE | 4199.1 | 22356.71 | 3204.8 | FALSE
P038 | Canyon Renovation 38 | General Conditions | 57260.51 | FALSE | FALSE | 1523.47 | 63044.65 | -5784.14 | FALSE
P063 | Summit Office 63 | General Conditions | 96790.61 | FALSE | FALSE | 12232.7 | 97591.54 | -800.93 | FALSE
P080 | Aspen Lodge 80 | Subcontractors | 122248 | FALSE | FALSE | 6120.34 | 93722.5 | 28525.5 | FALSE
P085 | Summit Residences 85 | Subcontractors | 243066.81 | FALSE | FALSE | 27307.21 | 192487.09 | 50579.72 | FALSE
P087 | Copper Office 87 | Permits & Fees | 70006.25 | FALSE | FALSE | 4533.93 | 27890.75 | 42115.5 | FALSE
P063 | Summit Office 63 | Equipment | 43102.76 | FALSE | FALSE | 4066.1 | 40631.05 | 2471.71 | FALSE
P016 | Wasatch Lodge 16 | Other | 13586.52 | FALSE | FALSE | 2219.55 | 12869.9 | 716.62 | FALSE
P021 | Copper Center 21 | Materials | 663513.56 | FALSE | FALSE | 189201.43 | 564301.71 | 99211.85 | FALSE
P026 | Granite Commons 26 | Other | 89576.08 | FALSE | FALSE | 0 | 85307.05 | 4269.03 | FALSE
P029 | Copper Center 29 | Other | 16947.64 | FALSE | FALSE | 1730.5 | 14513.98 | 2433.66 | FALSE
P033 | Bonneville Retail 33 | Other | 25515 | FALSE | FALSE | 1858.78 | 25420.05 | 94.95 | FALSE
P036 | Bonneville Commons 36 | Equipment | 106390 | FALSE | FALSE | 9462.23 | 94887.39 | 11502.61 | FALSE
P036 | Bonneville Commons 36 | General Conditions | 170224 | FALSE | FALSE | 23835.55 | 146184.36 | 24039.64 | FALSE
P041 | Canyon Office 41 | Other | 29968.68 | FALSE | FALSE | 8238.28 | 18296.24 | 11672.44 | FALSE
P049 | Wasatch Commons 49 | Other | 31527.15 | FALSE | FALSE | 0 | 31545.75 | -18.6 | FALSE
P053 | Wasatch Center 53 | Equipment | 77329.48 | FALSE | FALSE | 12339.49 | 64897.56 | 12431.92 | FALSE
P053 | Wasatch Center 53 | General Conditions | 123632.14 | FALSE | FALSE | 15100.43 | 110402.66 | 13229.48 | FALSE
P062 | Granite Residences 62 | Materials | 707829 | FALSE | FALSE | 33385.15 | 785779.44 | -77950.44 | FALSE
P064 | Juniper Commons 64 | Equipment | 67439.15 | FALSE | FALSE | 5417 | 61789.87 | 5649.28 | FALSE
P067 | Copper Office 67 | Subcontractors | 183312.98 | FALSE | FALSE | 35940.22 | 147539.47 | 35773.51 | FALSE
P072 | Aspen Office 72 | Subcontractors | 317623.34 | FALSE | FALSE | 20249.37 | 337621.22 | -19997.88 | FALSE
P073 | Canyon Commons 73 | Subcontractors | 509301 | FALSE | FALSE | 0 | 544952.73 | -35651.73 | FALSE
P076 | Granite Center 76 | Equipment | 53821.22 | FALSE | FALSE | 8452.38 | 40802.3 | 13018.92 | FALSE
P076 | Granite Center 76 | General Conditions | 86219.03 | FALSE | FALSE | 2176.47 | 74979.83 | 11239.2 | FALSE
P092 | Copper Retail 92 | Subcontractors | 252303.91 | FALSE | FALSE | 4169.03 | 236518.91 | 15785 | FALSE
P093 | Granite Office 93 | Permits & Fees | 73737 | FALSE | FALSE | 0 | 51547.42 | 22189.58 | FALSE
P094 | Copper Commons 94 | Permits & Fees | 108258.62 | FALSE | FALSE | 4949.72 | 49809.26 | 58449.36 | FALSE
P007 | Wasatch Renovation 07 | Subcontractors | 665265.48 | FALSE | FALSE | 40240.4 | 688745.63 | -23480.15 | FALSE
P015 | Juniper Residences 15 | Materials | 271423.91 | FALSE | FALSE | 60855.1 | 227449.49 | 43974.42 | FALSE
P020 | Wasatch Commons 20 | Materials | 242420.46 | FALSE | FALSE | 36711.33 | 210077.99 | 32342.47 | FALSE
P031 | Summit Lodge 31 | Other | 15930 | FALSE | FALSE | 0 | 15883.45 | 46.55 | FALSE
P035 | Aspen Office 35 | Materials | 250056 | FALSE | FALSE | 41671.57 | 226838.29 | 23217.71 | FALSE
P044 | Copper Medical 44 | Other | 13812 | FALSE | FALSE | 0 | 14288.5 | -476.5 | FALSE
P055 | Canyon Lodge 55 | Permits & Fees | 50972 | FALSE | FALSE | 3990.12 | 51021.49 | -49.49 | FALSE
P064 | Juniper Commons 64 | General Conditions | 107970.58 | FALSE | FALSE | 23156.09 | 83612.04 | 24358.54 | FALSE
P065 | Aspen Lodge 65 | Permits & Fees | 27144 | FALSE | FALSE | 3696.49 | 24937.15 | 2206.85 | FALSE
P042 | Juniper Residences 42 | Permits & Fees | 81840.64 | FALSE | FALSE | 0 | 85389.36 | -3548.72 | FALSE
P057 | Juniper Commons 57 | Subcontractors | 221704 | FALSE | FALSE | 0 | 225221.85 | -3517.85 | FALSE
P007 | Wasatch Renovation 07 | Other | 43310.04 | FALSE | FALSE | 3365.48 | 44979.64 | -1669.6 | FALSE
P015 | Juniper Residences 15 | Permits & Fees | 41794.81 | FALSE | FALSE | 0 | 45901.82 | -4107.01 | FALSE
P026 | Granite Commons 26 | Subcontractors | 820490.49 | FALSE | FALSE | 55238.98 | 747150.17 | 73340.32 | FALSE
P028 | Copper Office 28 | Equipment | 9318.57 | FALSE | FALSE | 515.3 | 9131.95 | 186.62 | FALSE
P028 | Copper Office 28 | General Conditions | 20748.28 | FALSE | FALSE | 2247.2 | 18304.56 | 2443.72 | FALSE
P029 | Copper Center 29 | Subcontractors | 264269.1 | FALSE | FALSE | 38794.69 | 232338.22 | 31930.88 | FALSE
P031 | Summit Lodge 31 | Subcontractors | 164610 | FALSE | FALSE | 23517.41 | 157977.99 | 6632.01 | FALSE
P033 | Bonneville Retail 33 | Subcontractors | 238140 | FALSE | FALSE | 0 | 232077.93 | 6062.07 | FALSE
P035 | Aspen Office 35 | Permits & Fees | 41676 | FALSE | FALSE | 746.47 | 41166.17 | 509.83 | FALSE
P041 | Canyon Office 41 | Subcontractors | 462561.19 | FALSE | FALSE | 41864.01 | 437965.7 | 24595.49 | FALSE
P042 | Juniper Residences 42 | Materials | 503890.31 | FALSE | FALSE | 28596.83 | 552811.92 | -48921.61 | FALSE
P043 | Granite Medical 43 | Equipment | 46094.36 | FALSE | FALSE | 0 | 46541.32 | -446.96 | FALSE
P043 | Granite Medical 43 | General Conditions | 73786.27 | FALSE | FALSE | 0 | 79383.99 | -5597.72 | FALSE
P049 | Wasatch Commons 49 | Subcontractors | 323548.42 | FALSE | FALSE | 31859.71 | 325202.1 | -1653.68 | FALSE
P051 | Aspen Retail 51 | Equipment | 17128 | FALSE | FALSE | 0 | 17060.41 | 67.59 | FALSE
P051 | Aspen Retail 51 | General Conditions | 38538 | FALSE | FALSE | 0 | 40102.79 | -1564.79 | FALSE
P055 | Canyon Lodge 55 | Materials | 305832 | FALSE | FALSE | 0 | 343817.66 | -37985.66 | FALSE
P056 | Wasatch Office 56 | General Conditions | 31842.56 | FALSE | FALSE | 6031.41 | 23806.79 | 8035.77 | FALSE
P057 | Juniper Commons 57 | Other | 23754 | FALSE | FALSE | 1212.19 | 22085.57 | 1668.43 | FALSE
P062 | Granite Residences 62 | Permits & Fees | 138478.81 | FALSE | FALSE | 8545.13 | 154137.57 | -15658.76 | FALSE
P069 | Bonneville Retail 69 | Equipment | 34658.32 | FALSE | FALSE | 820.52 | 35943.21 | -1284.89 | FALSE
P072 | Aspen Office 72 | Other | 20855.95 | FALSE | FALSE | 2301.03 | 18142.15 | 2713.8 | FALSE
P092 | Copper Retail 92 | Other | 24326.56 | FALSE | FALSE | 1831.67 | 19099.17 | 5227.39 | FALSE
P094 | Copper Commons 94 | Materials | 533977.98 | FALSE | FALSE | 0 | 277083.35 | 256894.63 | FALSE
P016 | Wasatch Lodge 16 | Subcontractors | 141399.6 | FALSE | FALSE | 14614.96 | 139662.72 | 1736.88 | FALSE
P020 | Wasatch Commons 20 | Permits & Fees | 21900.28 | FALSE | FALSE | 461.8 | 21513.04 | 387.24 | FALSE
P021 | Copper Center 21 | Permits & Fees | 59570.6 | FALSE | FALSE | 10074.37 | 52652.49 | 6918.11 | FALSE
P044 | Copper Medical 44 | Subcontractors | 128912 | FALSE | FALSE | 8296.68 | 128464.46 | 447.54 | FALSE
P056 | Wasatch Office 56 | Equipment | 14243.34 | FALSE | FALSE | 878.48 | 12785.66 | 1457.68 | FALSE
P060 | Canyon Retail 60 | General Conditions | 96862.42 | FALSE | FALSE | 2610.8 | 93392.09 | 3470.33 | FALSE
P065 | Aspen Lodge 65 | Materials | 162864 | FALSE | FALSE | 7911.78 | 162401.98 | 462.02 | FALSE
P067 | Copper Office 67 | Other | 17629.25 | FALSE | FALSE | 1002.59 | 15807.95 | 1821.3 | FALSE
P069 | Bonneville Retail 69 | General Conditions | 55392.54 | FALSE | FALSE | 3470.37 | 55820.47 | -427.93 | FALSE
P073 | Canyon Commons 73 | Other | 56589 | FALSE | FALSE | 367.97 | 64404.93 | -7815.93 | FALSE
P093 | Granite Office 93 | Materials | 712791 | FALSE | FALSE | 48861.7 | 517322.37 | 195468.63 | FALSE
P060 | Canyon Retail 60 | Equipment | 68913.45 | FALSE | FALSE | 5038.63 | 63984.82 | 4928.63 | FALSE
P005 | Summit Residences 05 | Equipment | 97204.03 | FALSE | FALSE | 2360.05 | 98663.05 | -1459.02 | FALSE
P005 | Summit Residences 05 | General Conditions | 169660.71 | FALSE | FALSE | 31821.09 | 160850.27 | 8810.44 | FALSE
P016 | Wasatch Lodge 16 | Materials | 111232.41 | FALSE | FALSE | 10636.72 | 114441.48 | -3209.07 | FALSE
P020 | Wasatch Commons 20 | Other | 21900.27 | FALSE | FALSE | 4666.45 | 16144.45 | 5755.82 | FALSE
P021 | Copper Center 21 | Other | 59570.59 | FALSE | FALSE | 10966.57 | 46538.42 | 13032.17 | FALSE
P026 | Granite Commons 26 | Materials | 886036.18 | FALSE | FALSE | 159179.62 | 770936.61 | 115099.57 | FALSE
P031 | Summit Lodge 31 | Materials | 127440 | FALSE | FALSE | 11193.79 | 127665.76 | -225.76 | FALSE
P033 | Bonneville Retail 33 | Materials | 212625 | FALSE | FALSE | 0 | 223127.49 | -10502.49 | FALSE
P035 | Aspen Office 35 | Other | 31257 | FALSE | FALSE | 718.89 | 29174.94 | 2082.06 | FALSE
P041 | Canyon Office 41 | Materials | 421514.89 | FALSE | FALSE | 32312.9 | 429917.36 | -8402.47 | FALSE
P042 | Juniper Residences 42 | Subcontractors | 641651.7 | FALSE | FALSE | 0 | 693869.02 | -52217.32 | FALSE
P044 | Copper Medical 44 | Materials | 115100 | FALSE | FALSE | 10980.55 | 109915.16 | 5184.84 | FALSE
P049 | Wasatch Commons 49 | Materials | 246578.27 | FALSE | FALSE | 13346.55 | 270619.77 | -24041.5 | FALSE
P055 | Canyon Lodge 55 | Subcontractors | 395033 | FALSE | FALSE | 49827.24 | 370635.24 | 24397.76 | FALSE
P057 | Juniper Commons 57 | Permits & Fees | 31672 | FALSE | FALSE | 1870.07 | 28703.1 | 2968.9 | FALSE
P061 | Summit Center 61 | General Conditions | 166262.1 | FALSE | FALSE | 26006.88 | 162618.64 | 3643.46 | FALSE
P062 | Granite Residences 62 | Other | 49782.81 | FALSE | FALSE | 3540.48 | 44189 | 5593.81 | FALSE
P067 | Copper Office 67 | Permits & Fees | 23385.26 | FALSE | FALSE | 512.24 | 22925.76 | 459.5 | FALSE
P068 | Aspen Lodge 68 | Equipment | 34018.68 | FALSE | FALSE | 0 | 35400.87 | -1382.19 | FALSE
P072 | Aspen Office 72 | Permits & Fees | 56923.95 | FALSE | FALSE | 3694.53 | 61844.71 | -4920.76 | FALSE
P073 | Canyon Commons 73 | Permits & Fees | 56589 | FALSE | FALSE | 0 | 58760.24 | -2171.24 | FALSE
P079 | Canyon Center 79 | General Conditions | 102144 | FALSE | FALSE | 19961.12 | 79438.98 | 22705.02 | FALSE
P086 | Copper Center 86 | Equipment | 16076 | FALSE | FALSE | 1153.19 | 8529.3 | 7546.7 | FALSE
P086 | Copper Center 86 | General Conditions | 36171 | FALSE | FALSE | 2186.23 | 22095.72 | 14075.28 | FALSE
P088 | Copper Center 88 | Equipment | 35087.84 | FALSE | FALSE | 2767.24 | 26801.74 | 8286.1 | FALSE
P088 | Copper Center 88 | General Conditions | 56147.73 | FALSE | FALSE | 0 | 47402.57 | 8745.16 | FALSE
P090 | Canyon Office 90 | General Conditions | 64605.86 | FALSE | FALSE | 2255.23 | 59761.4 | 4844.46 | FALSE
P093 | Granite Office 93 | Subcontractors | 663633 | FALSE | FALSE | 103488.03 | 393700.83 | 269932.17 | FALSE
P094 | Copper Commons 94 | Subcontractors | 580491.42 | FALSE | FALSE | 13456.49 | 268409.53 | 312081.89 | FALSE
P007 | Wasatch Renovation 07 | Permits & Fees | 123890.04 | FALSE | FALSE | 33957.7 | 111243.03 | 12647.01 | FALSE
P015 | Juniper Residences 15 | Other | 31607.8 | FALSE | FALSE | 0 | 30835.07 | 772.73 | FALSE
P029 | Copper Center 29 | Materials | 235686.2 | FALSE | FALSE | 56588.84 | 211362.76 | 24323.44 | FALSE
P061 | Summit Center 61 | Equipment | 94933.66 | FALSE | FALSE | 8178.91 | 90709.51 | 4224.15 | FALSE
P065 | Aspen Lodge 65 | Subcontractors | 210366 | FALSE | FALSE | 20931.93 | 200597.55 | 9768.45 | FALSE
P068 | Aspen Lodge 68 | General Conditions | 59393.46 | FALSE | FALSE | 2104 | 59665.7 | -272.24 | FALSE
P079 | Canyon Center 79 | Equipment | 63840 | FALSE | FALSE | 3818.77 | 56417.11 | 7422.89 | FALSE
P092 | Copper Retail 92 | Permits & Fees | 32337.55 | FALSE | FALSE | 1477.09 | 27644.82 | 4692.73 | FALSE
P090 | Canyon Office 90 | Equipment | 45886.72 | FALSE | FALSE | 1175.11 | 40380.09 | 5506.63 | FALSE
P004 | Juniper Medical 04 | Equipment | 36525.69 | FALSE | FALSE | 850.3 | 35997.9 | 527.79 | FALSE
P004 | Juniper Medical 04 | General Conditions | 81190.15 | FALSE | FALSE | 4882.14 | 74625.37 | 6564.78 | FALSE
P013 | Aspen Renovation 13 | Equipment | 88696 | FALSE | FALSE | 4220.32 | 83152.82 | 5543.18 | FALSE
P013 | Aspen Renovation 13 | General Conditions | 155218 | FALSE | FALSE | 13243.15 | 160742.62 | -5524.62 | FALSE
P021 | Copper Center 21 | Subcontractors | 433132.56 | FALSE | FALSE | 104465.38 | 389688.63 | 43443.93 | FALSE
P024 | Aspen Retail 24 | Equipment | 47053.07 | FALSE | FALSE | 14002 | 32820.39 | 14232.68 | FALSE
P024 | Aspen Retail 24 | General Conditions | 104744.12 | FALSE | FALSE | 5203.96 | 104693.45 | 50.67 | FALSE
P026 | Granite Commons 26 | Permits & Fees | 89576.07 | FALSE | FALSE | 6900.8 | 79592.18 | 9983.89 | FALSE
P029 | Copper Center 29 | Permits & Fees | 52423.64 | FALSE | FALSE | 0 | 58222.64 | -5799 | FALSE
P035 | Aspen Office 35 | Subcontractors | 322989 | FALSE | FALSE | 19831.34 | 323908.29 | -919.29 | FALSE
P041 | Canyon Office 41 | Permits & Fees | 87952.68 | FALSE | FALSE | 0 | 91326.07 | -3373.39 | FALSE
P042 | Juniper Residences 42 | Other | 61701.64 | FALSE | FALSE | 5454.01 | 58155.55 | 3546.09 | FALSE
P045 | Bonneville Office 45 | Equipment | 47040 | FALSE | FALSE | 0 | 42217.08 | 4822.92 | FALSE
P045 | Bonneville Office 45 | General Conditions | 105840 | FALSE | FALSE | 16035.86 | 80572.56 | 25267.44 | FALSE
P055 | Canyon Lodge 55 | Other | 38229 | FALSE | FALSE | 2454.44 | 40646.03 | -2417.03 | FALSE
P057 | Juniper Commons 57 | Materials | 197950 | FALSE | FALSE | 9205.06 | 202929.38 | -4979.38 | FALSE
P062 | Granite Residences 62 | Subcontractors | 760763.97 | FALSE | FALSE | 70082.97 | 768041.15 | -7277.18 | FALSE
P065 | Aspen Lodge 65 | Other | 20358 | FALSE | FALSE | 791.23 | 20442.96 | -84.96 | FALSE
P072 | Aspen Office 72 | Materials | 297627.22 | FALSE | FALSE | 58604.54 | 310028.95 | -12401.73 | FALSE
P073 | Canyon Commons 73 | Materials | 547027 | FALSE | FALSE | 130621.81 | 457181.57 | 89845.43 | FALSE
P092 | Copper Retail 92 | Materials | 196960.79 | FALSE | FALSE | 0 | 188123.41 | 8837.38 | FALSE
P093 | Granite Office 93 | Other | 73737 | FALSE | FALSE | 4116.23 | 50264.82 | 23472.18 | FALSE
P007 | Wasatch Renovation 07 | Materials | 612380.57 | FALSE | FALSE | 0 | 732358.26 | -119977.69 | FALSE
P011 | Granite Residences 11 | Equipment | 41500 | FALSE | FALSE | 9957.66 | 32698.7 | 8801.3 | FALSE
P015 | Juniper Residences 15 | Subcontractors | 299367.89 | FALSE | FALSE | 79704.66 | 237134.51 | 62233.38 | FALSE
P016 | Wasatch Lodge 16 | Permits & Fees | 18009.53 | FALSE | FALSE | 0 | 18290.24 | -280.71 | FALSE
P020 | Wasatch Commons 20 | Subcontractors | 157299.26 | FALSE | FALSE | 0 | 161604.05 | -4304.79 | FALSE
P033 | Bonneville Retail 33 | Permits & Fees | 34020 | FALSE | FALSE | 6399.4 | 28165.63 | 5854.37 | FALSE
P052 | Summit Medical 52 | Equipment | 64943.8 | FALSE | FALSE | 1868.85 | 61603.9 | 3339.9 | FALSE
P052 | Summit Medical 52 | General Conditions | 113407 | FALSE | FALSE | 6777.7 | 109320.64 | 4086.36 | FALSE
P067 | Copper Office 67 | Materials | 143924.13 | FALSE | FALSE | 32167.44 | 114352.02 | 29572.11 | FALSE
P011 | Granite Residences 11 | General Conditions | 66400 | FALSE | FALSE | 1437.5 | 63584.13 | 2815.87 | FALSE
P031 | Summit Lodge 31 | Permits & Fees | 21240 | FALSE | FALSE | 1602.22 | 20659.71 | 580.29 | FALSE
P044 | Copper Medical 44 | Permits & Fees | 18416 | FALSE | FALSE | 3936.06 | 14495.13 | 3920.87 | FALSE
P094 | Copper Commons 94 | Other | 37778.63 | FALSE | FALSE | 402.32 | 15459.27 | 22319.36 | FALSE
P049 | Wasatch Commons 49 | Permits & Fees | 42271.14 | FALSE | FALSE | 0 | 46231.09 | -3959.95 | FALSE
P007 | Wasatch Renovation 07 | Equipment | 85110.05 | FALSE | FALSE | 11280.37 | 74766.89 | 10343.16 | FALSE
P007 | Wasatch Renovation 07 | General Conditions | 148565.09 | FALSE | FALSE | 0 | 176846.02 | -28280.93 | FALSE
P011 | Granite Residences 11 | Materials | 199200 | FALSE | FALSE | 4393.52 | 214037.74 | -14837.74 | FALSE
P036 | Bonneville Commons 36 | Subcontractors | 659618 | FALSE | FALSE | 0 | 672597.61 | -12979.61 | FALSE
P043 | Granite Medical 43 | Other | 27691.92 | FALSE | FALSE | 3518.25 | 26338.37 | 1353.55 | FALSE
P051 | Aspen Retail 51 | Other | 12846 | FALSE | FALSE | 1758.42 | 10991.65 | 1854.35 | FALSE
P052 | Summit Medical 52 | Materials | 527379.21 | FALSE | FALSE | 0 | 543440.85 | -16061.64 | FALSE
P053 | Wasatch Center 53 | Subcontractors | 475451.35 | FALSE | FALSE | 82976.28 | 395221.45 | 80229.9 | FALSE
P056 | Wasatch Office 56 | Other | 10653.22 | FALSE | FALSE | 0 | 9799.97 | 853.25 | FALSE
P057 | Juniper Commons 57 | Equipment | 31672 | TRUE | FALSE | 3953.42 | 27412.31 | 4259.69 | FALSE
P057 | Juniper Commons 57 | General Conditions | 71262 | FALSE | FALSE | 14933.34 | 60207.48 | 11054.52 | FALSE
P060 | Canyon Retail 60 | Other | 41443.97 | FALSE | FALSE | 2949.24 | 36525.39 | 4918.58 | FALSE
P064 | Juniper Commons 64 | Subcontractors | 420976.33 | FALSE | FALSE | 34568.67 | 388991.64 | 31984.69 | FALSE
P067 | Copper Office 67 | Equipment | 29321.89 | FALSE | FALSE | 6012.69 | 23791.03 | 5530.86 | FALSE
P068 | Aspen Lodge 68 | Permits & Fees | 25374.78 | FALSE | FALSE | 0 | 25783.64 | -408.86 | FALSE
P069 | Bonneville Retail 69 | Other | 20734.22 | FALSE | FALSE | 1917.09 | 20794.19 | -59.97 | FALSE
P072 | Aspen Office 72 | Equipment | 40300.93 | FALSE | FALSE | 8784.44 | 32620.67 | 7680.26 | FALSE
P072 | Aspen Office 72 | General Conditions | 70173.88 | FALSE | FALSE | 20316.4 | 60422.85 | 9751.03 | FALSE
P073 | Canyon Commons 73 | Equipment | 94315 | FALSE | FALSE | 3419.56 | 102875.54 | -8560.54 | FALSE
P073 | Canyon Commons 73 | General Conditions | 132041 | FALSE | FALSE | 12916.81 | 134119.73 | -2078.73 | FALSE
P076 | Granite Center 76 | Subcontractors | 338104.94 | FALSE | FALSE | 38915.35 | 249809.78 | 88295.16 | FALSE
P079 | Canyon Center 79 | Permits & Fees | 51072 | FALSE | FALSE | 9321.07 | 35350.49 | 15721.51 | FALSE
P090 | Canyon Office 90 | Permits & Fees | 27623.15 | FALSE | FALSE | 0 | 24765.73 | 2857.42 | FALSE
P092 | Copper Retail 92 | Equipment | 40495.32 | FALSE | FALSE | 4050.71 | 35756.93 | 4738.39 | FALSE
P092 | Copper Retail 92 | General Conditions | 64821.87 | FALSE | FALSE | 0 | 64622.54 | 199.33 | FALSE
P004 | Juniper Medical 04 | Materials | 235801.39 | FALSE | FALSE | 7550.08 | 224161.34 | 11640.05 | FALSE
P005 | Summit Residences 05 | Permits & Fees | 141342.68 | FALSE | FALSE | 11073.09 | 139328.23 | 2014.45 | FALSE
P013 | Aspen Renovation 13 | Materials | 620872 | FALSE | FALSE | 135931.9 | 598047.73 | 22824.27 | FALSE
P024 | Aspen Retail 24 | Materials | 302601.79 | FALSE | FALSE | 98092.18 | 219863.72 | 82738.07 | FALSE
P028 | Copper Office 28 | Other | 6957.72 | FALSE | FALSE | 0 | 6354.38 | 603.34 | FALSE
P045 | Bonneville Office 45 | Materials | 294000 | FALSE | FALSE | 6654.55 | 283651.95 | 10348.05 | FALSE
P067 | Copper Office 67 | General Conditions | 46951.15 | FALSE | FALSE | 2241.84 | 45348.15 | 1603 | FALSE
P086 | Copper Center 86 | Permits & Fees | 16076 | FALSE | FALSE | 958.99 | 8825.4 | 7250.6 | FALSE
P088 | Copper Center 88 | Permits & Fees | 28055.89 | FALSE | FALSE | 3528.69 | 18916.3 | 9139.59 | FALSE
P061 | Summit Center 61 | Permits & Fees | 143682.44 | FALSE | FALSE | 36895.91 | 128812.06 | 14870.38 | FALSE
P005 | Summit Residences 05 | Materials | 700066.95 | FALSE | FALSE | 46433 | 760489.66 | -60422.71 | FALSE
P016 | Wasatch Lodge 16 | Equipment | 22591.29 | FALSE | FALSE | 2874.92 | 19589.58 | 3001.71 | FALSE
P024 | Aspen Retail 24 | Permits & Fees | 46410.05 | FALSE | FALSE | 3835.82 | 46513.85 | -103.8 | FALSE
P026 | Granite Commons 26 | General Conditions | 209540.68 | FALSE | FALSE | 19374.69 | 202176.68 | 7364 | FALSE
P028 | Copper Office 28 | Subcontractors | 65979.14 | FALSE | FALSE | 0 | 66740.96 | -761.82 | FALSE
P029 | Copper Center 29 | Equipment | 34290.46 | FALSE | FALSE | 0 | 37343.47 | -3053.01 | FALSE
P031 | Summit Lodge 31 | General Conditions | 42480 | FALSE | FALSE | 2868.51 | 44963.17 | -2483.17 | FALSE
P033 | Bonneville Retail 33 | General Conditions | 76545 | FALSE | FALSE | 0 | 80705.7 | -4160.7 | FALSE
P036 | Bonneville Commons 36 | Other | 63834 | FALSE | FALSE | 6209.37 | 59114.79 | 4719.21 | FALSE
P041 | Canyon Office 41 | Equipment | 59449.02 | FALSE | FALSE | 7055.42 | 51902.76 | 7546.26 | FALSE
P041 | Canyon Office 41 | General Conditions | 103913.7 | FALSE | FALSE | 6223.48 | 103305.21 | 608.49 | FALSE
P043 | Granite Medical 43 | Subcontractors | 287267.27 | FALSE | FALSE | 32516.26 | 264471.82 | 22795.45 | FALSE
P044 | Copper Medical 44 | Equipment | 18416 | FALSE | FALSE | 3126.88 | 15999.41 | 2416.59 | FALSE
P045 | Bonneville Office 45 | Permits & Fees | 47040 | FALSE | FALSE | 2010.9 | 41489.67 | 5550.33 | FALSE
P049 | Wasatch Commons 49 | Equipment | 52662.71 | FALSE | FALSE | 9989.94 | 45687 | 6975.71 | FALSE
P049 | Wasatch Commons 49 | General Conditions | 84189.85 | FALSE | FALSE | 20668.07 | 79995.36 | 4194.49 | FALSE
P051 | Aspen Retail 51 | Subcontractors | 119896 | FALSE | FALSE | 0 | 122322.65 | -2426.65 | FALSE
P053 | Wasatch Center 53 | Other | 46302.65 | FALSE | FALSE | 5777.64 | 43379.23 | 2923.42 | FALSE
P056 | Wasatch Office 56 | Subcontractors | 100406.04 | FALSE | FALSE | 4604.48 | 94329.92 | 6076.12 | FALSE
P060 | Canyon Retail 60 | Subcontractors | 377311.08 | FALSE | FALSE | 65196.49 | 321501.08 | 55810 | FALSE
P068 | Aspen Lodge 68 | Materials | 276604.53 | FALSE | FALSE | 0 | 295611.99 | -19007.46 | FALSE
P069 | Bonneville Retail 69 | Subcontractors | 212328.92 | FALSE | FALSE | 16994.84 | 217809.97 | -5481.05 | FALSE
P076 | Granite Center 76 | Other | 32397.8 | FALSE | FALSE | 3090.84 | 25384.98 | 7012.82 | FALSE
P086 | Copper Center 86 | Materials | 100475 | FALSE | FALSE | 2606.62 | 62992.08 | 37482.92 | FALSE
P088 | Copper Center 88 | Materials | 169054.29 | FALSE | FALSE | 28411.42 | 108353.25 | 60701.04 | FALSE
P090 | Canyon Office 90 | Materials | 272794.33 | FALSE | FALSE | 64453.95 | 198293.44 | 74500.89 | FALSE
P011 | Granite Residences 11 | Permits & Fees | 33200 | FALSE | FALSE | 3708.45 | 29529.48 | 3670.52 | FALSE
P016 | Wasatch Lodge 16 | General Conditions | 36177.81 | FALSE | FALSE | 6697.77 | 34487.93 | 1689.88 | FALSE
P026 | Granite Commons 26 | Equipment | 148763.61 | FALSE | FALSE | 19569.02 | 124786.35 | 23977.26 | FALSE
P029 | Copper Center 29 | General Conditions | 60107.09 | FALSE | FALSE | 7299 | 58841.56 | 1265.53 | FALSE
P044 | Copper Medical 44 | General Conditions | 41436 | FALSE | FALSE | 4138.17 | 38466.59 | 2969.41 | FALSE
P052 | Summit Medical 52 | Permits & Fees | 48463.2 | FALSE | FALSE | 2934.1 | 43753.43 | 4709.77 | FALSE
P064 | Juniper Commons 64 | Other | 40531.42 | FALSE | FALSE | 4303.15 | 31226.92 | 9304.5 | FALSE
P079 | Canyon Center 79 | Materials | 306432 | FALSE | FALSE | 53551.02 | 244014.88 | 62417.12 | FALSE
P004 | Juniper Medical 04 | Permits & Fees | 35958.46 | FALSE | FALSE | 1734.63 | 34549.22 | 1409.24 | FALSE
P033 | Bonneville Retail 33 | Equipment | 34020 | FALSE | FALSE | 0 | 31909.28 | 2110.72 | FALSE
P061 | Summit Center 61 | Materials | 658895.01 | FALSE | FALSE | 60703.73 | 713709.53 | -54814.52 | FALSE
P031 | Summit Lodge 31 | Equipment | 26550 | FALSE | FALSE | 466.1 | 28433.08 | -1883.08 | FALSE
P013 | Aspen Renovation 13 | Permits & Fees | 133044 | FALSE | FALSE | 19569.69 | 129434.93 | 3609.07 | FALSE
P004 | Juniper Medical 04 | Other | 27252.47 | FALSE | FALSE | 1286.96 | 23633.05 | 3619.42 | FALSE
P005 | Summit Residences 05 | Subcontractors | 760026.24 | FALSE | FALSE | 0 | 775461.62 | -15435.38 | FALSE
P011 | Granite Residences 11 | Other | 24900 | FALSE | FALSE | 0 | 23549.4 | 1350.6 | FALSE
P013 | Aspen Renovation 13 | Other | 44348 | FALSE | FALSE | 2971.02 | 43333.31 | 1014.69 | FALSE
P024 | Aspen Retail 24 | Other | 35129.06 | FALSE | FALSE | 6035.91 | 30018.45 | 5110.61 | FALSE
P028 | Copper Office 28 | Materials | 59895.42 | FALSE | FALSE | 13813.38 | 44129.04 | 15766.38 | FALSE
P036 | Bonneville Commons 36 | Permits & Fees | 85112 | FALSE | FALSE | 9993.49 | 70590.96 | 14521.04 | FALSE
P042 | Juniper Residences 42 | Equipment | 102621.97 | FALSE | FALSE | 6605.47 | 104714.78 | -2092.81 | FALSE
P042 | Juniper Residences 42 | General Conditions | 164323.61 | FALSE | FALSE | 6841.24 | 182088.2 | -17764.59 | FALSE
P043 | Granite Medical 43 | Materials | 224358.55 | FALSE | FALSE | 54601.87 | 170938.09 | 53420.46 | FALSE
P045 | Bonneville Office 45 | Other | 35280 | FALSE | FALSE | 2429.59 | 32729.01 | 2550.99 | FALSE
P051 | Aspen Retail 51 | Materials | 107050 | FALSE | FALSE | 7909.38 | 101056.18 | 5993.82 | FALSE
P052 | Summit Medical 52 | Other | 48463.19 | FALSE | FALSE | 769.07 | 46165.37 | 2297.82 | FALSE
P053 | Wasatch Center 53 | Permits & Fees | 62053.66 | FALSE | FALSE | 5718.64 | 58844.78 | 3208.88 | FALSE
P055 | Canyon Lodge 55 | General Conditions | 101944 | FALSE | FALSE | 22151.76 | 90966.01 | 10977.99 | FALSE
P056 | Wasatch Office 56 | Materials | 90572.6 | FALSE | FALSE | 1262.63 | 82904.31 | 7668.29 | FALSE
P060 | Canyon Retail 60 | Materials | 406698.5 | FALSE | FALSE | 35207.87 | 384352.27 | 22346.23 | FALSE
P061 | Summit Center 61 | Subcontractors | 733812.92 | FALSE | FALSE | 56245.74 | 733224.55 | 588.37 | FALSE
P065 | Aspen Lodge 65 | General Conditions | 54288 | FALSE | FALSE | 13196.97 | 46080.55 | 8207.45 | FALSE
P068 | Aspen Lodge 68 | Subcontractors | 176776.08 | FALSE | FALSE | 8512.66 | 169946.87 | 6829.21 | FALSE
P069 | Bonneville Retail 69 | Materials | 161011.46 | FALSE | FALSE | 25776.91 | 142366.77 | 18644.69 | FALSE
P076 | Granite Center 76 | Permits & Fees | 42846.81 | FALSE | FALSE | 4659.72 | 31863.64 | 10983.17 | FALSE
P079 | Canyon Center 79 | Subcontractors | 395808 | FALSE | FALSE | 98064.64 | 266570.52 | 129237.48 | FALSE
P086 | Copper Center 86 | Subcontractors | 112532 | FALSE | FALSE | 0 | 69482.88 | 43049.12 | FALSE
P088 | Copper Center 88 | Subcontractors | 217846.56 | FALSE | FALSE | 0 | 172246.95 | 45599.61 | FALSE
P090 | Canyon Office 90 | Subcontractors | 252708.47 | FALSE | FALSE | 25374.52 | 202395.35 | 50313.12 | FALSE
P093 | Granite Office 93 | Equipment | 122895 | FALSE | FALSE | 4740.46 | 88380.51 | 34514.49 | FALSE
P093 | Granite Office 93 | General Conditions | 172053 | FALSE | FALSE | 10404.09 | 125684.79 | 46368.21 | FALSE
P094 | Copper Commons 94 | General Conditions | 129686.56 | FALSE | FALSE | 11737.77 | 52931.53 | 76755.03 | FALSE
P055 | Canyon Lodge 55 | Equipment | 63715 | FALSE | FALSE | 4588.22 | 62249.79 | 1465.21 | FALSE
P064 | Juniper Commons 64 | Permits & Fees | 53815.43 | FALSE | FALSE | 6319.38 | 48104.19 | 5711.24 | FALSE
P065 | Aspen Lodge 65 | Equipment | 33930 | FALSE | FALSE | 2429.67 | 32275.24 | 1654.76 | FALSE
P094 | Copper Commons 94 | Equipment | 74287.94 | FALSE | FALSE | 4404 | 30172.78 | 44115.16 | FALSE
P004 | Juniper Medical 04 | Subcontractors | 259083.23 | FALSE | FALSE | 44585.17 | 226534.08 | 32549.15 | FALSE
P005 | Summit Residences 05 | Other | 49494.69 | FALSE | FALSE | 10037.28 | 43312.7 | 6181.99 | FALSE
P011 | Granite Residences 11 | Subcontractors | 257300 | FALSE | FALSE | 47909.5 | 240174.78 | 17125.22 | FALSE
P013 | Aspen Renovation 13 | Subcontractors | 687394 | FALSE | FALSE | 36979.93 | 665428.78 | 21965.22 | FALSE
P015 | Juniper Residences 15 | General Conditions | 94300.02 | FALSE | FALSE | 17063.14 | 86464.67 | 7835.35 | FALSE
P020 | Wasatch Commons 20 | Equipment | 29475.92 | FALSE | FALSE | 0 | 30454.32 | -978.4 | FALSE
P021 | Copper Center 21 | Equipment | 80305.4 | FALSE | FALSE | 15463.99 | 74658.69 | 5646.71 | FALSE
P021 | Copper Center 21 | General Conditions | 139875.99 | FALSE | FALSE | 23151.78 | 132683.88 | 7192.11 | FALSE
P028 | Copper Office 28 | Permits & Fees | 9193.71 | FALSE | FALSE | 696.3 | 8330.96 | 862.75 | FALSE
P035 | Aspen Office 35 | General Conditions | 83352 | FALSE | FALSE | 17361.71 | 67811.59 | 15540.41 | FALSE
P043 | Granite Medical 43 | Permits & Fees | 36804.91 | FALSE | FALSE | 1848.04 | 34379.38 | 2425.53 | FALSE
P045 | Bonneville Office 45 | Subcontractors | 329280 | FALSE | FALSE | 0 | 298974.86 | 30305.14 | FALSE
P052 | Summit Medical 52 | Subcontractors | 336462.21 | FALSE | FALSE | 69078.46 | 275775.51 | 60686.7 | FALSE
P053 | Wasatch Center 53 | Materials | 362818.48 | FALSE | FALSE | 42616.99 | 350613.36 | 12205.12 | FALSE
P056 | Wasatch Office 56 | Permits & Fees | 14126.23 | FALSE | FALSE | 310.19 | 13376.74 | 749.49 | FALSE
P060 | Canyon Retail 60 | Permits & Fees | 41443.97 | FALSE | FALSE | 3037.87 | 38590.86 | 2853.11 | FALSE
P062 | Granite Residences 62 | Equipment | 96848.22 | FALSE | FALSE | 0 | 103925.6 | -7077.38 | FALSE
P062 | Granite Residences 62 | General Conditions | 168805.03 | FALSE | FALSE | 25383.31 | 170589.6 | -1784.57 | FALSE
P064 | Juniper Commons 64 | Materials | 329686.91 | FALSE | FALSE | 0 | 321240.91 | 8446 | FALSE
P076 | Granite Center 76 | Materials | 267588.97 | FALSE | FALSE | 13211.55 | 231448.59 | 36140.38 | FALSE
P079 | Canyon Center 79 | Other | 38304 | FALSE | FALSE | 6667.13 | 30416.52 | 7887.48 | FALSE
P015 | Juniper Residences 15 | Equipment | 42318.21 | FALSE | FALSE | 2439.53 | 42339.42 | -21.21 | FALSE
P035 | Aspen Office 35 | Equipment | 52095 | FALSE | FALSE | 5491.67 | 48165.49 | 3929.51 | FALSE
P061 | Summit Center 61 | Other | 47210.43 | FALSE | FALSE | 2666.47 | 41993.82 | 5216.61 | FALSE
P068 | Aspen Lodge 68 | Other | 25374.78 | FALSE | FALSE | 1228.11 | 22304.4 | 3070.38 | FALSE
P086 | Copper Center 86 | Other | 12057 | FALSE | FALSE | 1091.93 | 5882.53 | 6174.47 | FALSE
P088 | Copper Center 88 | Other | 21059.89 | FALSE | FALSE | 806.95 | 16191.17 | 4868.72 | FALSE
P090 | Canyon Office 90 | Other | 27623.14 | FALSE | FALSE | 2830.23 | 21544.32 | 6078.82 | FALSE
P020 | Wasatch Commons 20 | General Conditions | 51376.2 | FALSE | FALSE | 4466.76 | 47575.37 | 3800.83 | FALSE
P024 | Aspen Retail 24 | Subcontractors | 333229.66 | FALSE | FALSE | 13480.33 | 331922.3 | 1307.36 | FALSE
P036 | Bonneville Commons 36 | Materials | 510672 | FALSE | FALSE | 59816.42 | 468806.01 | 41865.99 | FALSE
P051 | Aspen Retail 51 | Permits & Fees | 17128 | FALSE | FALSE | 0 | 16888.32 | 239.68 | FALSE
P069 | Bonneville Retail 69 | Permits & Fees | 27848.22 | FALSE | FALSE | 743.22 | 27929.94 | -81.72 | FALSE
P997 |  | Labor | 42000 | FALSE | TRUE | 0 | 0 | 42000 | TRUE

## Project Summary
Project Budget vs Actual - June 30, 2026
P997 has no matching master project record; totals include its $42,000 budget.
project_id | Sum of revised_budget | Sum of incurred_cost | Sum of pending_exposure | Sum of budget_remaining
P001 | 1154930.57 | 1177455.59 | 24996.87 | -22525.02
P002 | 663600 | 638239.17 | 36654.28 | 25360.83
P003 | 1509036.96 | 1421961.44 | 53945.13 | 87075.52
P004 | 927323.09 | 872697.08 | 60889.28 | 54626.01
P005 | 2474734.23 | 2624103.54 | 101724.51 | -149369.31
P006 | 1285700 | 1272404.1 | 64718.33 | 13295.9
P007 | 2165501.79 | 2393915.73 | 88843.95 | -228413.94
P008 | 2319000 | 2293222.12 | 134111.49 | 25777.88
P009 | 553600 | 575122.01 | 40356.49 | -21522.01
P010 | 587790.38 | 546572.55 | 22273.73 | 41217.83
P011 | 830000 | 832088.47 | 67406.63 | -2088.47
P012 | 1138064.45 | 1083674.9 | 145762.04 | 54389.55
P013 | 2217400 | 2228568.9 | 212916.01 | -11168.9
P014 | 2438200 | 2524501.68 | 84807.23 | -86301.68
P015 | 1071040.34 | 976945.5 | 160062.43 | 94094.84
P016 | 458176.28 | 468079.92 | 37043.92 | -9903.64
P017 | 1260793.12 | 1308537.06 | 100517.57 | -47743.94
P018 | 1211300 | 1232870.32 | 115026.29 | -21570.32
P019 | 423940.65 | 441360.2 | 34562.68 | -17419.55
P020 | 757563.93 | 728212.02 | 46306.34 | 29351.91
P021 | 2073479.86 | 2014233.66 | 353323.52 | 59246.2
P022 | 2989672.68 | 2822847.6 | 308204.53 | 166825.08
P023 | 2552700 | 2699149.28 | 144693.86 | -146449.28
P024 | 1192402.46 | 1128475.14 | 140650.2 | 63927.32
P025 | 2269346.51 | 2183534.66 | 217488.15 | 85811.85
P026 | 3038853.68 | 2857957.99 | 260263.11 | 180895.69
P027 | 1765972.65 | 1735069.79 | 186618.9 | 30902.86
P028 | 236085.69 | 219591.39 | 17272.18 | 16494.3
P029 | 847381.87 | 814129.51 | 104413.03 | 33252.36
P030 | 1831501.37 | 1708619.92 | 231851.4 | 122881.45
P031 | 531000 | 543041.85 | 39648.03 | -12041.85
P032 | 1849089.97 | 2033343.83 | 97366.62 | -184253.86
P033 | 850500 | 848174.39 | 8258.18 | 2325.61
P034 | 537400 | 513646 | 69869.84 | 23754
P035 | 1041900 | 1006808 | 85821.65 | 35092
P036 | 2127800 | 2057515.58 | 109317.06 | 70284.42
P037 | 994626.33 | 928955.67 | 135034.27 | 65670.66
P038 | 642650.22 | 678078.46 | 23344.92 | -35428.24
P039 | 580900 | 599908.71 | 18521.6 | -19008.71
P040 | 1064777.77 | 999514.52 | 49503.59 | 65263.25
P041 | 1498434.03 | 1486807.21 | 95694.09 | 11626.82
P042 | 2078132.21 | 2273129.31 | 47497.55 | -194997.1
P043 | 928945.46 | 861589.1 | 92484.42 | 67356.36
P044 | 460400 | 457577.89 | 30478.34 | 2822.11
P045 | 1176000 | 1084344 | 27130.9 | 91656
P046 | 1027183.74 | 1026156.22 | 91158.02 | 1027.52
P047 | 2261400 | 2195699.28 | 135520.92 | 65700.72
P048 | 523567.94 | 532596.57 | 30180.81 | -9028.63
P049 | 1039157.1 | 1100140.44 | 75864.27 | -60983.34
P050 | 1078754.91 | 1117510.19 | 73014.98 | -38755.28
P051 | 428200 | 433595.86 | 9667.8 | -5395.86
P052 | 1648060.02 | 1651201.97 | 81428.18 | -3141.95
P053 | 1527582.76 | 1441327.18 | 164529.47 | 86255.58
P054 | 417571.3 | 399216.85 | 2975.83 | 18354.45
P055 | 1274300 | 1344771.28 | 83011.78 | -70471.28
P056 | 359011.26 | 331885.82 | 13087.19 | 27125.44
P057 | 791800 | 792104.82 | 31174.08 | -304.82
P058 | 396100 | 389854.51 | 17059.47 | 6245.49
P059 | 520500 | 531568.85 | 39755.27 | -11068.85
P060 | 1397448.43 | 1304538.99 | 114040.9 | 92909.44
P061 | 2360521.92 | 2468218.33 | 190697.64 | -107696.41
P062 | 2489140.62 | 2655296.58 | 140937.04 | -166155.96
P063 | 1080292.16 | 1104070.77 | 88702.18 | -23778.61
P064 | 1362371.58 | 1297858.88 | 73764.29 | 64512.7
P065 | 678600 | 674909.21 | 48958.07 | 3690.79
P066 | 596118.64 | 534972.88 | 35086.28 | 61145.76
P067 | 593662.9 | 519309.44 | 77877.02 | 74353.46
P068 | 864389.17 | 890175.89 | 11844.77 | -25786.72
P069 | 681010.82 | 692104.38 | 49722.95 | -11093.56
P070 | 1245975.29 | 1339350.64 | 43682.57 | -93375.35
P071 | 658823.04 | 674763.92 | 35750.43 | -15940.88
P072 | 1042797.57 | 1102251.42 | 113950.31 | -59453.85
P073 | 1886300 | 1943210.82 | 147326.15 | -56910.82
P074 | 1299500 | 1251433.85 | 67556.46 | 48066.15
P075 | 2086600 | 2010784.1 | 57085.97 | 75815.9
P076 | 1097440.52 | 913676.48 | 70506.31 | 183764.04
P077 | 896945.86 | 691020.75 | 84859.62 | 205925.11
P078 | 1244999.45 | 1046268.43 | 44632.13 | 198731.02
P079 | 1276800 | 1007513.15 | 191383.75 | 269286.85
P080 | 436600 | 339826.16 | 23290.39 | 96773.84
P081 | 756500 | 527951.12 | 41987.59 | 228548.88
P082 | 1545279.14 | 1457701.82 | 73863.57 | 87577.32
P083 | 1115000 | 1121480.89 | 28894.37 | -6480.89
P084 | 917500 | 730068.5 | 81659.82 | 187431.5
P085 | 900247.43 | 813023.23 | 42534.44 | 87224.2
P086 | 401900 | 248358.36 | 7996.96 | 153541.64
P087 | 2341362.63 | 1016526.72 | 71882.31 | 1324835.91
P088 | 703194.65 | 531133.49 | 35514.3 | 172061.16
P089 | 978700 | 127226.01 | 7164.77 | 851473.99
P090 | 935957.28 | 790517.76 | 96089.04 | 145439.52
P091 | 1850308.33 | 1615819.1 | 84357.65 | 234489.23
P092 | 815777.46 | 768236.86 | 11528.5 | 47540.6
P093 | 2457900 | 1720860.62 | 171610.51 | 737039.38
P094 | 1888931.2 | 904391.81 | 34950.3 | 984539.39
P095 | 530000 | 397469.14 | 30577.71 | 132530.86
P096 | 2207100 | 669547.59 | 53277.32 | 1537552.41
P997 | 42000 | 0 | 0 | 42000
Grand Total | 119564833.67 | 111386073.69 | 7961647.6 | 8178759.98

## Report Notes
Report Notes
This table summarizes revised budget, incurred costs through June 30, 2026—including employee payroll—pending exposure, and budget remaining for each project. Budget remaining equals revised budget minus incurred costs. It does not estimate remaining work costs or establish whether a project will finish within budget.
Revised budgets are taken from the supplied budget file, which has no effective dates or version history. We cannot confirm that these budgets were valid as of June 30, 2026.
Pending exposure is shown separately. It is not included in incurred costs or deducted from budget remaining.
P997 has no matching record in the master project table. Its revised budget of $42,000 remains included in this workbook’s budget totals.
BUD-P057-04 has a missing original budget, which remains NULL (unknown) and should not be interpreted as zero.
Some project–cost category combinations have no matching cost transactions or employee labor records through June 30, 2026. Zero recorded costs may reflect no activity or missing records; they do not prove no costs were incurred.